## Start Here
From: LeanTakt team
Download the free PDF

## Takt Elements
Project Name
2024 | [52 empty] | 2025
Cold Winter Months | [43 empty] | Cold Winter Months | [51 empty] | Cold Winter Months
JANUARY |  |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  |  | MAY |  |  |  | JUNE |  |  |  | JULY |  |  |  |  | AUGUST |  |  |  | SEPTEMBER |  |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  | DECEMBER |  |  |  |  | JANUARY |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUGUST |  |  |  | SEPTEMBER |  |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  | DECEMBER
 | time axis 2024-01-01 to 2025-12-29
INTERIORS LEGEND
[43 empty] | SOIL DISTURBANCE PERMIT | [29 empty] | 1 | Wall Layout + Top Track
[46 empty] | MAKE SAFE UTILITIES | [26 empty] | 2 | Fire Sprinkler + Priority Walls
[48 empty] | MOBILIZATION | [24 empty] | 3 | OH Ductwork
[50 empty] | EXCAVATION | [5 empty] | BIM LEGEND | [16 empty] | 4 | OH Branch Conduits and Lighting
[51 empty] | SHORING | [5 empty] | Model Coordination | [15 empty] | 5 | OH Mechanical Piping
[53 empty] | PIERS |  |  |  | Prepare Shop Drawings + Layout Drawings | [15 empty] | 6 | OH Electrical
[57 empty] | Shop Drawing Approval | [15 empty] | 7 | Wall Framing
[42 empty] | UG BIM Coordination | [14 empty] | Prefabrication of Material | [15 empty] | 8 | In wall Rough-in
[73 empty] | 9 | Soffits + Ceilings
[39 empty] | Shaft Prep | [33 empty] | 10 | Soffit & Ceiling Rough
[43 empty] | Elevator Cabs | [29 empty] | 11 | Drywall
[57 empty] | Test + Certification | [15 empty] | 12 | Taping
[39 empty] | Erect Stair | [33 empty] | 13 | Prime + First Coat
[43 empty] | Pour Stair Pans | [29 empty] | 14 | Data Cabling
[73 empty] | 15 | Ceiling Grid
[41 empty] | Temp Roof |  |  |  |  | Install Swing Stages | [26 empty] | 16 | Casework + Doors
[50 empty] | Set AHU & Install | [22 empty] | 17 | MEP Trim / Light and Devices
[55 empty] | Roofing | [17 empty] | 18 | Flooring + Baseboards
[73 empty] | 19 | Final Paint
[73 empty] | 20 | Final Accessories
[46 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | [5 empty] | 21 | Pre-Punch & Clean
[73 empty] | 22 | Punchlist
More colors
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | [15 empty] | 1 | 2 | 3 | 4 | 5 | 6 | [8 empty] | 7 | 8 | 9 | 10 | 11 | 12 | [8 empty] | 13 | 14 | B | 15 | 16 | PI
[10 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | [15 empty] | 1 | 2 | 3 | 4 | 5 | 6 | [8 empty] | 7 | 8 | 9 | 10 | 11 | 12 | [8 empty] | 13 | 14 | IR | 15 | 16 | PI
[11 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | [15 empty] | 1 | 2 | 3 | 4 | 5 | 6 | [8 empty] | 7 | 8 | 9 | 10 | 11 | 12 |  |  |  |  | B |  |  |  | 13 | 14 | IR | B | 16 | PI
[12 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | [15 empty] | 1 | 2 | 3 | 4 | 5 | 6 | [8 empty] | 7 | 8 | 9 | 10 | 11 | 12 | [8 empty] | 13 | 14 | IR | 15 | 16 | PI
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | [15 empty] | 1 | 2 | 3 | 4 | 5 | 6 | [8 empty] | 7 | 8 | 9 | 10 | 11 | 12 | [8 empty] | 13 | 14 | IR | 15 | 16 | PI
[14 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | [15 empty] | 1 | 2 | 3 | 4 | 5 | 6 | [8 empty] | 7 | 8 | 9 | 10 | 11 | 12 | [8 empty] | 13 | 14 | IR | 15 | 16 | PI
[15 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
[16 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
[17 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | [7 empty] | 1 | 2 | 3 | 4 | 5 | [9 empty] | 6 | 7 | 8 | 9 | 10 | [9 empty] | 11 | 12 | 13 | 14 | 15
[38 empty] | 1 | 2 | 3 | 4 | 5 | [9 empty] | 6 | 7 | 8 | 9 | 10 | [9 empty] | 11 | 12 | 13 | 14 | 15
[39 empty] | 1 | 2 | 3 | 4 | 5 | [9 empty] | 6 | 7 | 8 | 9 | 10 | [9 empty] | 11 | 12 | 13 | 14 | 15
[40 empty] | 1 | 2 | 3 | 4 | 5 | [9 empty] | 6 | 7 | 8 | 9 | 10 | [9 empty] | 11 | 12 | 13 | 14 | 15
[41 empty] | 1 | 2 | 3 | 4 | 5 | [9 empty] | 6 | 7 | 8 | 9 | 10 | [9 empty] | 11 | 12 | 13 | 14 | 15
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 |  |  | 13 13 13 12 11 10 9 8 7: A; 13 13 13 13 12 11 10 9 8: B; 13 13 13 13 13 12 11 10 9: C; 13 13 13 13 13 13 12 11 10: D; 13 13 13 13 13 13 13 12 11: E; 13 13 13 13 13 13 13 13 12: F
[10 empty] | 1 | 2 | 3 | 4 | 5 | 6 |  | 13 13 13 13 12 11 10 9 8: A; 13 13 13 13 13 12 11 10 9: B; 13 13 13 13 13 13 12 11 10: C; 13 13 13 13 13 13 13 12 11: D; 13 13 13 13 13 13 13 13 12: E; 13 13 13 13 13 13 13 13 13: F
[11 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 13 13 13 13 13 12 11 10 9: A; 13 13 13 13 13 13 12 11 10: B; 13 13 13 13 13 13 13 12 11: C; 13 13 13 13 13 13 13 13 12: D; 13 13 13 13 13 13 13 13 13: E | F
[12 empty] | 1 | 2 | 3 | 4 | 5 | 9 8 7 6 5 4 3 2 1: 6; 13 13 13 13 13 13 12 11 10: A; 13 13 13 13 13 13 13 12 11: B; 13 13 13 13 13 13 13 13 12: C; 13 13 13 13 13 13 13 13 13: D | E | F
[13 empty] | 1 | 2 | 3 | 4 | 9 8 7 6 5 4 3 2 1: 5; 10 9 8 7 6 5 4 3 2: 6; 13 13 13 13 13 13 13 12 11: A; 13 13 13 13 13 13 13 13 12: B; 13 13 13 13 13 13 13 13 13: C | D | E | F
[14 empty] | 1 | 2 | 3 | 9 8 7 6 5 4 3 2 1: 4; 10 9 8 7 6 5 4 3 2: 5; 11 10 9 8 7 6 5 4 3: 6; 13 13 13 13 13 13 13 13 12: A; 13 13 13 13 13 13 13 13 13: B | C | D | E | F
Interiors
Finishes
Logistics Map
LEVEL 3
LEVEL 2
LEVEL 1
TARGET SUBSTANTIAL COMPLETION
POWER ON
AC ON
4 Week Look Ahead
Color palettes You can copy these colors for your takt's format
Examples of how to format line items, trains or one-off activities
Shapes Use for Phase Titles, Maps Titles, Logic Ties, Milestones, etc.

## Full MACRO - Example
|  |  | 2022 | [51 empty] | 2023 | [51 empty] | 2024
|  |  | Cold Winter Months | [21 empty] | Hot Summer Months | [21 empty] | Cold Winter Months | [29 empty] | Hot Summer Months | [21 empty] | Cold Winter Months
|  |  | JANUARY |  |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  | MAY |  |  |  |  | JUNE |  |  |  | JULY |  |  |  | AUGUST |  |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  |  | NOVEMBER |  |  |  | DECEMBER |  |  |  | JANUARY |  |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  | MAY |  |  |  |  | JUNE |  |  |  | JULY |  |  |  |  | AUGUST |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  |  | NOVEMBER |  |  |  | DECEMBER |  |  |  | JANUARY |  |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  |  | MAY |  |  |  | JUNE |  |  |  | JULY
|  |  | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10 | 2023-07-17 | 2023-07-24 | 2023-07-31 | 2023-08-07 | 2023-08-14 | 2023-08-21 | 2023-08-28 | 2023-09-04 | 2023-09-11 | 2023-09-18 | 2023-09-25 | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30 | 2023-11-06 | 2023-11-13 | 2023-11-20 | 2023-11-27 | 2023-12-04 | 2023-12-11 | 2023-12-18 | 2023-12-25 | 2024-01-01 | 2024-01-08 | 2024-01-15 | 2024-01-22 | 2024-01-29 | 2024-02-05 | 2024-02-12 | 2024-02-19 | 2024-02-26 | 2024-03-04 | 2024-03-11 | 2024-03-18 | 2024-03-25 | 2024-04-01 | 2024-04-08 | 2024-04-15 | 2024-04-22 | 2024-04-29 | 2024-05-06 | 2024-05-13 | 2024-05-20 | 2024-05-27 | 2024-06-03 | 2024-06-10 | 2024-06-17 | 1900-01-23 | 1899-12-31 | 1900-01-07 | 15 | 22 | 29
|  | MILESTONES | SEPTEMBER 2022-09-05: Exteriors Phase Pull Plan
[24 empty] | Sitework Complete | [10 empty] | Foundation Complete | [16 empty] | Structure complete | [18 empty] | Air On |  |  |  |  | Final Sitework Pull Plan | [7 empty] | Interior Complete
[29 empty] | Structure Phase Pull Plan | [16 empty] | Interiors Phase Pull Plan | [20 empty] | Power On | [5 empty] | Exterior Complete
|  | PROCUREMENT | AUGUST 2022-08-22: Electrical Gear; JANUARY 2023-01-30: SES Fit-out & Energize
HVAC Equipment
Windows
[49 empty] | H |  |  |  |  | H
[49 empty] | H |  |  |  |  | H
[49 empty] | H |  |  |  |  | H
[9 empty] | Entire Site | MOB |  | 1H | 1H | 1H | 1I | 1I | 1I | 1I | 1J | 1J | 1J | 1J | 1K | [25 empty] | H |  |  |  |  | H
BEGINNING SITEWORK WORK |  |  | MAY 2022-05-23: ZONE A; MAY 2022-05-30: F1; JUNE 2022-06-06: F1; JUNE 2022-06-13: F2; JUNE 2022-06-20: F2; JUNE 2022-06-27: F3; JULY 2022-07-04: F3; JULY 2022-07-11: F4; JULY 2022-07-18: F4; JULY 2022-07-25: F4; AUGUST 2022-08-01: B; AUGUST 2022-08-08: B; NOVEMBER 2022-11-21: H; DECEMBER 2022-12-26: H
1H | Excavation/Grading |  | JUNE 2022-06-06: ZONE B; JUNE 2022-06-13: F1; JUNE 2022-06-20: F1; JUNE 2022-06-27: F2; JULY 2022-07-04: F2; JULY 2022-07-11: F3; JULY 2022-07-18: F3; JULY 2022-07-25: F4; AUGUST 2022-08-01: F4; AUGUST 2022-08-08: F4; AUGUST 2022-08-15: B; AUGUST 2022-08-22: B; NOVEMBER 2022-11-21: H; DECEMBER 2022-12-26: H
1I | Install Storm/Sanitary/Water/Dry U.G. Utilities | bar: NOVEMBER 2022-11-21; DECEMBER 2022-12-26
1J | Parking Area Base Stone | bar: NOVEMBER 2022-11-21; DECEMBER 2022-12-26
1K | Final Grading |  | FEBRUARY 2022-02-14: NTP; AUGUST 2022-08-08: LEVEL 1A; AUGUST 2022-08-15: S1; AUGUST 2022-08-22: S1; AUGUST 2022-08-29: S1; SEPTEMBER 2022-09-05: S2; SEPTEMBER 2022-09-12: S2; SEPTEMBER 2022-09-19: S3; SEPTEMBER 2022-09-26: S4; OCTOBER 2022-10-03: S4; NOVEMBER 2022-11-21: H; DECEMBER 2022-12-26: H; AUGUST 2023-08-21: Substantial Completion; SEPTEMBER 2023-09-18: Final Completion + Financial Completion
[35 empty] | LEVEL 1B | S1 | S1 | S1 | S2 | S2 | S3 | S4 | S4 | [5 empty] | H |  |  |  |  | H
[36 empty] | LEVEL 2A | S1 | S1 | S1 | S2 | S2 | S3 | S4 | S4 |  |  |  |  | H |  |  |  |  | H
[37 empty] | LEVEL 2B | S1 | S1 | S1 | S2 | S2 | S3 | S4 | S4 |  |  |  | H |  |  |  |  | H
FOUNDATION LEGEND |  |  | SEPTEMBER 2022-09-05: LEVEL 3A; SEPTEMBER 2022-09-12: S1; SEPTEMBER 2022-09-19: S1; SEPTEMBER 2022-09-26: S1; OCTOBER 2022-10-03: S2; OCTOBER 2022-10-10: S2; OCTOBER 2022-10-17: S3; OCTOBER 2022-10-24: S4; OCTOBER 2022-10-31: S4; NOVEMBER 2022-11-21: H; DECEMBER 2022-12-26: H
F1 | Excavate & Pour Footings |  | SEPTEMBER 2022-09-12: LEVEL 3B; SEPTEMBER 2022-09-19: S1; SEPTEMBER 2022-09-26: S1; OCTOBER 2022-10-03: S1; OCTOBER 2022-10-10: S2; OCTOBER 2022-10-17: S2; OCTOBER 2022-10-24: S3; OCTOBER 2022-10-31: S4; NOVEMBER 2022-11-07: S4; NOVEMBER 2022-11-21: H; DECEMBER 2022-12-26: H
F2 | Columns & Walls |  | SEPTEMBER 2022-09-19: LEVEL 4A; SEPTEMBER 2022-09-26: S1; OCTOBER 2022-10-03: S1; OCTOBER 2022-10-10: S1; OCTOBER 2022-10-17: S2; OCTOBER 2022-10-24: S2; OCTOBER 2022-10-31: S3; NOVEMBER 2022-11-07: S4; NOVEMBER 2022-11-14: S4; NOVEMBER 2022-11-21: H; DECEMBER 2022-12-26: H
F3 | UG MEP |  | SEPTEMBER 2022-09-26: LEVEL 4B; OCTOBER 2022-10-03: S1; OCTOBER 2022-10-10: S1; OCTOBER 2022-10-17: S1; OCTOBER 2022-10-24: S2; OCTOBER 2022-10-31: S2; NOVEMBER 2022-11-07: S3; NOVEMBER 2022-11-14: S4; NOVEMBER 2022-11-21: H; DECEMBER 2022-12-26: H
F4 | SOG |  | OCTOBER 2022-10-03: LEVEL 5A; OCTOBER 2022-10-10: S1; OCTOBER 2022-10-17: S1; OCTOBER 2022-10-24: S1; OCTOBER 2022-10-31: S2; NOVEMBER 2022-11-07: S2; NOVEMBER 2022-11-14: S3; NOVEMBER 2022-11-21: H; NOVEMBER 2022-11-28: S4; DECEMBER 2022-12-26: H
B | Buffer |  | OCTOBER 2022-10-10: LEVEL 5B; OCTOBER 2022-10-17: S1; OCTOBER 2022-10-24: S1; OCTOBER 2022-10-31: S1; NOVEMBER 2022-11-07: S2; NOVEMBER 2022-11-14: S2; NOVEMBER 2022-11-21: H; NOVEMBER 2022-11-28: S4; DECEMBER 2022-12-05: S4; DECEMBER 2022-12-12: B; DECEMBER 2022-12-26: H
[49 empty] | H |  |  |  |  | H
[49 empty] | H |  |  |  |  | H
[49 empty] | H |  |  | ZONE 1A | 1 | H | 2 | 3 | 4 | 5 | 6 | B | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
STRUCTURE LEGEND |  |  | NOVEMBER 2022-11-21: H; DECEMBER 2022-12-19: ZONE 1B; DECEMBER 2022-12-26: H; JANUARY 2023-01-02: 1; JANUARY 2023-01-09: 2; JANUARY 2023-01-16: 3; JANUARY 2023-01-23: 4; JANUARY 2023-01-30: 5; FEBRUARY 2023-02-06: 6; FEBRUARY 2023-02-13: B; FEBRUARY 2023-02-20: 7; FEBRUARY 2023-02-27: 8; MARCH 2023-03-06: 9; MARCH 2023-03-13: 10; MARCH 2023-03-20: 11; MARCH 2023-03-27: 12; APRIL 2023-04-03: 13; APRIL 2023-04-10: 14; APRIL 2023-04-17: 15
S1 | Deck Formwork | bar: NOVEMBER 2022-11-21; DECEMBER 2022-12-26
S2 | Deck MEP & Reinforcing |  | NOVEMBER 2022-11-21: H; JANUARY 2023-01-02: ZONE 2A; JANUARY 2023-01-09: 1; JANUARY 2023-01-16: 2; JANUARY 2023-01-23: 3; JANUARY 2023-01-30: 4; FEBRUARY 2023-02-06: 5; FEBRUARY 2023-02-13: 6; FEBRUARY 2023-02-20: B; FEBRUARY 2023-02-27: 7; MARCH 2023-03-06: 8; MARCH 2023-03-13: 9; MARCH 2023-03-20: 10; MARCH 2023-03-27: 11; APRIL 2023-04-03: 12; APRIL 2023-04-10: 13; APRIL 2023-04-17: 14; APRIL 2023-04-24: 15
S3 | Deck Inspections & Place |  | NOVEMBER 2022-11-21: H; JANUARY 2023-01-09: ZONE 2B; JANUARY 2023-01-16: 1; JANUARY 2023-01-23: 2; JANUARY 2023-01-30: 3; FEBRUARY 2023-02-06: 4; FEBRUARY 2023-02-13: 5; FEBRUARY 2023-02-20: 6; FEBRUARY 2023-02-27: B; MARCH 2023-03-06: 7; MARCH 2023-03-13: 8; MARCH 2023-03-20: 9; MARCH 2023-03-27: 10; APRIL 2023-04-03: 11; APRIL 2023-04-10: 12; APRIL 2023-04-17: 13; APRIL 2023-04-24: 14; MAY 2023-05-01: 15
S4 | Columns & Walls |  | NOVEMBER 2022-11-21: H; DECEMBER 2022-12-26: H; JANUARY 2023-01-16: ZONE 2C; JANUARY 2023-01-23: 1; JANUARY 2023-01-30: 2; FEBRUARY 2023-02-06: 3; FEBRUARY 2023-02-13: 4; FEBRUARY 2023-02-20: 5; FEBRUARY 2023-02-27: 6; MARCH 2023-03-06: B; MARCH 2023-03-13: 7; MARCH 2023-03-20: 8; MARCH 2023-03-27: 9; APRIL 2023-04-03: 10; APRIL 2023-04-10: 11; APRIL 2023-04-17: 12; APRIL 2023-04-24: 13; MAY 2023-05-01: 14; MAY 2023-05-08: 15
[49 empty] | H |  |  |  |  | H |  |  |  | ZONE 2D | 1 | 2 | 3 | 4 | 5 | 6 | B | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[49 empty] | H |  |  |  |  | H |  |  |  |  | ZONE 2E | 1 | 2 | 3 | 4 | 5 | 6 | B | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[49 empty] | H |  |  |  |  | H
[49 empty] | H |  |  |  |  | H | [5 empty] | ZONE 3A | 1 | 2 | 3 | 4 | 5 | 6 | B | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
EXTERIOR LEGEND |  |  | NOVEMBER 2022-11-21: H; DECEMBER 2022-12-26: H; FEBRUARY 2023-02-13: ZONE 3B; FEBRUARY 2023-02-20: 1; FEBRUARY 2023-02-27: 2; MARCH 2023-03-06: 3; MARCH 2023-03-13: 4; MARCH 2023-03-20: 5; MARCH 2023-03-27: 6; APRIL 2023-04-03: B; APRIL 2023-04-10: 7; APRIL 2023-04-17: 8; APRIL 2023-04-24: 9; MAY 2023-05-01: 10; MAY 2023-05-08: 11; MAY 2023-05-15: 12; MAY 2023-05-22: 13; MAY 2023-05-29: 14; JUNE 2023-06-05: 15
A | Structural Steel Supports |  | NOVEMBER 2022-11-21: H; DECEMBER 2022-12-26: H; FEBRUARY 2023-02-20: ZONE 3C; FEBRUARY 2023-02-27: 1; MARCH 2023-03-06: 2; MARCH 2023-03-13: 3; MARCH 2023-03-20: 4; MARCH 2023-03-27: 5; APRIL 2023-04-03: 6; APRIL 2023-04-10: B; APRIL 2023-04-17: 7; APRIL 2023-04-24: 8; MAY 2023-05-01: 9; MAY 2023-05-08: 10; MAY 2023-05-15: 11; MAY 2023-05-22: 12; MAY 2023-05-29: 13; JUNE 2023-06-05: 14; JUNE 2023-06-12: 15
B | Framing & Sheathing | bar: NOVEMBER 2022-11-21; DECEMBER 2022-12-26
C | EIFS |  | NOVEMBER 2022-11-21: H; DECEMBER 2022-12-26: H; FEBRUARY 2023-02-27: ZONE 4A; MARCH 2023-03-06: 1; MARCH 2023-03-13: 2; MARCH 2023-03-20: 3; MARCH 2023-03-27: 4; APRIL 2023-04-03: 5; APRIL 2023-04-10: 6; APRIL 2023-04-17: B; APRIL 2023-04-24: 7; MAY 2023-05-01: 8; MAY 2023-05-08: 9; MAY 2023-05-15: 10; MAY 2023-05-22: 11; MAY 2023-05-29: 12; JUNE 2023-06-05: 13; JUNE 2023-06-12: 14; JUNE 2023-06-19: 15
D | Window Installation |  | NOVEMBER 2022-11-21: H; DECEMBER 2022-12-26: H; MARCH 2023-03-06: ZONE 4B; MARCH 2023-03-13: 1; MARCH 2023-03-20: 2; MARCH 2023-03-27: 3; APRIL 2023-04-03: 4; APRIL 2023-04-10: 5; APRIL 2023-04-17: 6; APRIL 2023-04-24: B; MAY 2023-05-01: 7; MAY 2023-05-08: 8; MAY 2023-05-15: 9; MAY 2023-05-22: 10; MAY 2023-05-29: 11; JUNE 2023-06-05: 12; JUNE 2023-06-12: 13; JUNE 2023-06-19: 14; JUNE 2023-06-26: 15
E | Final Caulking & Finishes |  | NOVEMBER 2022-11-21: H; DECEMBER 2022-12-26: H; MARCH 2023-03-13: ZONE 4C; MARCH 2023-03-20: 1; MARCH 2023-03-27: 2; APRIL 2023-04-03: 3; APRIL 2023-04-10: 4; APRIL 2023-04-17: 5; APRIL 2023-04-24: 6; MAY 2023-05-01: B; MAY 2023-05-08: 7; MAY 2023-05-15: 8; MAY 2023-05-22: 9; MAY 2023-05-29: 10; JUNE 2023-06-05: 11; JUNE 2023-06-12: 12; JUNE 2023-06-19: 13; JUNE 2023-06-26: 14; JULY 2023-07-03: 15
F | Shade Structure |  | NOVEMBER 2022-11-21: H; DECEMBER 2022-12-26: H; MARCH 2023-03-20: ZONE 4D; MARCH 2023-03-27: 1; APRIL 2023-04-03: 2; APRIL 2023-04-10: 3; APRIL 2023-04-17: 4; APRIL 2023-04-24: 5; MAY 2023-05-01: 6; MAY 2023-05-08: B; MAY 2023-05-15: 7; MAY 2023-05-22: 8; MAY 2023-05-29: 9; JUNE 2023-06-05: 10; JUNE 2023-06-12: 11; JUNE 2023-06-19: 12; JUNE 2023-06-26: 13; JULY 2023-07-03: 14; JULY 2023-07-10: 15
[49 empty] | H |  |  |  |  | H
[49 empty] | H |  |  |  |  | H | [12 empty] | ZONE 5A | 1 | 2 | 3 | 4 | 5 | 6 | B | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | B
[49 empty] | H |  |  |  |  | H
INTERIOR LEGEND |  |  | NOVEMBER 2022-11-21: H; DECEMBER 2022-12-26: H; FEBRUARY 2023-02-13: Shaft Prep; MARCH 2023-03-27: Elevator Cabs; MAY 2023-05-08: Certification
1 | Remove Reshores, Floor Prep & Wall Layout |  | NOVEMBER 2022-11-21: H; DECEMBER 2022-12-05: Erect Stair 1; DECEMBER 2022-12-26: H; JANUARY 2023-01-09: Erect Stair 2; JUNE 2023-06-05: Comeback Areas for Elev
2 | Fire Sprinkler & Install Walls |  | NOVEMBER 2022-11-21: H; DECEMBER 2022-12-26: H; JANUARY 2023-01-09: Pour 1; FEBRUARY 2023-02-06: Pour 2
3 | OH Mechanical Duct | bar: NOVEMBER 2022-11-21; DECEMBER 2022-12-26
4 | OH Mech Equip, Piping, Branch Lines & Plumbing | bar: NOVEMBER 2022-11-21; DECEMBER 2022-12-26
5 | OH Electrical & Frame Walls |  | NOVEMBER 2022-11-21: H; DECEMBER 2022-12-26: H; JUNE 2023-06-05: Pre-functional Checklists; JUNE 2023-06-12: B
6 | Frame Walls, Install In-wall Electrical & Plumbing |  | NOVEMBER 2022-11-21: H; DECEMBER 2022-12-26: H; JULY 2023-07-03: Controls
7 | In-wall Process Piping, 1st Drywall, Insulation & Insp |  | OCTOBER 2022-10-24: WEST A; OCTOBER 2022-10-31: A; NOVEMBER 2022-11-07: A; NOVEMBER 2022-11-14: B; NOVEMBER 2022-11-21: H; NOVEMBER 2022-11-28: B; DECEMBER 2022-12-05: B; DECEMBER 2022-12-12: C; DECEMBER 2022-12-19: C; DECEMBER 2022-12-26: H; JANUARY 2023-01-02: D; JANUARY 2023-01-09: D; JANUARY 2023-01-16: E; JANUARY 2023-01-23: E; JULY 2023-07-24: TAB
8 | Finish Walls & Painting |  | NOVEMBER 2022-11-07: WEST B; NOVEMBER 2022-11-14: A; NOVEMBER 2022-11-21: H; NOVEMBER 2022-11-28: A; DECEMBER 2022-12-05: B; DECEMBER 2022-12-12: B; DECEMBER 2022-12-19: B; DECEMBER 2022-12-26: H; JANUARY 2023-01-02: C; JANUARY 2023-01-09: C; JANUARY 2023-01-16: D; JANUARY 2023-01-23: D; JANUARY 2023-01-30: E; FEBRUARY 2023-02-06: E; AUGUST 2023-08-07: Cx + FA Testing
9 | Painting & Install Ceiling Grid |  | NOVEMBER 2022-11-28: EAST A; DECEMBER 2022-12-05: A; DECEMBER 2022-12-12: A; DECEMBER 2022-12-19: B; DECEMBER 2022-12-26: H; JANUARY 2023-01-02: B; JANUARY 2023-01-09: B; JANUARY 2023-01-16: C; JANUARY 2023-01-23: C; JANUARY 2023-01-30: D; FEBRUARY 2023-02-06: D; FEBRUARY 2023-02-13: E; FEBRUARY 2023-02-20: E; AUGUST 2023-08-07: LS/ FA Testing
10 | Install Electrical Fixtures & Mech Ceiling Drops |  | NOVEMBER 2022-11-21: H; DECEMBER 2022-12-12: EAST B; DECEMBER 2022-12-19: A; DECEMBER 2022-12-26: H; JANUARY 2023-01-02: A; JANUARY 2023-01-09: B; JANUARY 2023-01-16: B; JANUARY 2023-01-23: B; JANUARY 2023-01-30: C; FEBRUARY 2023-02-06: C; FEBRUARY 2023-02-13: D; FEBRUARY 2023-02-20: D; FEBRUARY 2023-02-27: E; MARCH 2023-03-06: E; AUGUST 2023-08-21: Functional Performance Testing
11 | Remaining Ceiling Drops & Install Casework |  | NOVEMBER 2022-11-21: H; JANUARY 2023-01-02: NORTH A; JANUARY 2023-01-09: A; JANUARY 2023-01-16: A; JANUARY 2023-01-23: B; JANUARY 2023-01-30: B; FEBRUARY 2023-02-06: B; FEBRUARY 2023-02-13: C; FEBRUARY 2023-02-20: C; FEBRUARY 2023-02-27: D; MARCH 2023-03-06: D; MARCH 2023-03-13: E; MARCH 2023-03-20: E
12 | Countertops, Millwork & Final Paint |  | NOVEMBER 2022-11-21: H; DECEMBER 2022-12-26: H; JANUARY 2023-01-16: NORTH B; JANUARY 2023-01-23: A; JANUARY 2023-01-30: A; FEBRUARY 2023-02-06: B; FEBRUARY 2023-02-13: B; FEBRUARY 2023-02-20: B; FEBRUARY 2023-02-27: C; MARCH 2023-03-06: C; MARCH 2023-03-13: D; MARCH 2023-03-20: D; MARCH 2023-03-27: E; APRIL 2023-04-03: E
13 | Wall & Casework Fixtures, Ceiling Tiles & Flooring |  | NOVEMBER 2022-11-21: H; DECEMBER 2022-12-26: H; JANUARY 2023-01-30: SOUTH A; FEBRUARY 2023-02-06: A; FEBRUARY 2023-02-13: A; FEBRUARY 2023-02-20: B; FEBRUARY 2023-02-27: B; MARCH 2023-03-06: B; MARCH 2023-03-13: C; MARCH 2023-03-20: C; MARCH 2023-03-27: D; APRIL 2023-04-03: D; APRIL 2023-04-10: E; APRIL 2023-04-17: E
14 | Flooring, Final Paint & 1st Clean |  | NOVEMBER 2022-11-21: H; DECEMBER 2022-12-26: H; FEBRUARY 2023-02-13: SOUTH B; FEBRUARY 2023-02-20: A; FEBRUARY 2023-02-27: A; MARCH 2023-03-06: B; MARCH 2023-03-13: B; MARCH 2023-03-20: B; MARCH 2023-03-27: C; APRIL 2023-04-03: C; APRIL 2023-04-10: D; APRIL 2023-04-17: D; APRIL 2023-04-24: E; MAY 2023-05-01: E
15 | Punchlist, Corrections & Final Clean | bar: NOVEMBER 2022-11-21; DECEMBER 2022-12-26
[49 empty] | H |  |  |  |  | H |  |  |  |  | Roofing Area A | [13 empty] | F | F | F | F | F
[49 empty] | H |  |  |  |  | H | [7 empty] | Roofing Area B
[49 empty] | H |  |  |  |  | H
FINISHING SITEWORK LEGEND |  |  | NOVEMBER 2022-11-21: H; DECEMBER 2022-12-26: H; FEBRUARY 2023-02-27: Set AHU
1 | Site Demoblization |  | NOVEMBER 2022-11-21: H; DECEMBER 2022-12-26: H; MARCH 2023-03-13: Mechanical Installation
2 | UG Electrical |  | NOVEMBER 2022-11-21: H; DECEMBER 2022-12-26: H; MARCH 2023-03-27: Controls; JUNE 2023-06-05: AREA A; JUNE 2023-06-12: 1; JUNE 2023-06-19: 2; JUNE 2023-06-26: 3; JULY 2023-07-03: 4; JULY 2023-07-10: 5; JULY 2023-07-17: 6; JULY 2023-07-24: 7; JULY 2023-07-31: 8
3 | Rough Grading |  | NOVEMBER 2022-11-21: H; DECEMBER 2022-12-26: H; APRIL 2023-04-10: Point to Point; JUNE 2023-06-12: AREA B; JUNE 2023-06-19: 1; JUNE 2023-06-26: 2; JULY 2023-07-03: 3; JULY 2023-07-10: 4; JULY 2023-07-17: 5; JULY 2023-07-24: 6; JULY 2023-07-31: 7; AUGUST 2023-08-07: 8
4 | Hardscaping |  | NOVEMBER 2022-11-21: H; DECEMBER 2022-12-26: H; APRIL 2023-04-17: Mech Startup; JUNE 2023-06-19: AREA C; JUNE 2023-06-26: 1; JULY 2023-07-03: 2; JULY 2023-07-10: 3; JULY 2023-07-17: 4; JULY 2023-07-24: 5; JULY 2023-07-31: 6; AUGUST 2023-08-07: 7; AUGUST 2023-08-14: 8; AUGUST 2023-08-21: B
5 | Trees & Irrigation | bar: NOVEMBER 2022-11-21; DECEMBER 2022-12-26
6 | Landscaping | bar: NOVEMBER 2022-11-21; DECEMBER 2022-12-26
7 | Paving
8 | Site Finishes
Exteriors
Interiors
Structure
Sitework
Foundations
Neuroscience Institute Takt Plan
POWER ON
AIR ON

## Full NORM - Example
2023
|  |  | February | [19 empty] | March | [19 empty] | April | [19 empty] | May | [24 empty] | June | [19 empty] | July | [19 empty] | August | [24 empty] | September | [19 empty] | October | [24 empty] | November | [19 empty] | December | [19 empty] | January | [21 empty] | February | [19 empty] | March | [22 empty] | April | [19 empty] | May | [22 empty] | June | [21 empty] | July | [20 empty] | August | [22 empty] | September | [20 empty] | October | [21 empty] | November | [21 empty] | December
|  |  | 2022-02-07 |  |  |  |  | 2022-02-14 |  |  |  |  | 2022-02-21 |  |  |  |  | 2022-02-28 |  |  |  |  | 2022-03-07 |  |  |  |  | 2022-03-14 |  |  |  |  | 2022-03-21 |  |  |  |  | 2022-03-28 |  |  |  |  | 2022-04-04 |  |  |  |  | 2022-04-11 |  |  |  |  | 2022-04-18 |  |  |  |  | 2022-04-25 |  |  |  |  | 2022-05-02 |  |  |  |  | 2022-05-09 |  |  |  |  | 2022-05-16 |  |  |  |  | 2022-05-23 |  |  |  |  | 2022-05-30 |  |  |  |  | 2022-06-06 |  |  |  |  | 2022-06-13 |  |  |  |  | 2022-06-20 |  |  |  |  | 2022-06-27 |  |  |  |  | 2022-07-04 |  |  |  |  | 2022-07-11 |  |  |  |  | 2022-07-18 |  |  |  |  | 2022-07-25 |  |  |  |  | 2022-08-01 |  |  |  |  | 2022-08-08 |  |  |  |  | 2022-08-15 |  |  |  |  | 2022-08-22 |  |  |  |  | 2022-08-29 |  |  |  |  | 2022-09-05 |  |  |  |  | 2022-09-12 |  |  |  |  | 2022-09-19 |  |  |  |  | 2022-09-26 |  |  |  |  | 2022-10-03 |  |  |  |  | 2022-10-10 |  |  |  |  | 2022-10-17 |  |  |  |  | 2022-10-24 |  |  |  |  | 2022-10-31 |  |  |  |  | 2022-11-07 |  |  |  |  | 2022-11-14 |  |  |  |  | 2022-11-21 |  |  |  |  | 2022-11-28 |  |  |  |  | 2022-12-05 |  |  |  |  | 2022-12-12 |  |  |  |  | 2022-12-19 |  |  |  |  | 2022-12-26 |  |  |  |  | 2023-01-02 |  |  |  |  | 2023-01-09 |  |  |  |  | 2023-01-16 |  |  |  |  | 2023-01-23 |  |  |  |  | 2023-01-30 |  |  |  |  | 2023-02-06 |  |  |  |  | 2023-02-13 |  |  |  |  | 2023-02-20 |  |  |  |  | 2023-02-27 |  |  |  |  | 2023-03-06 |  |  |  |  | 2023-03-13 |  |  |  |  | 2023-03-20 |  |  |  |  | 2023-03-27 |  |  |  |  | 2023-04-03 |  |  |  |  | 2023-04-10 |  |  |  |  | 2023-04-17 |  |  |  |  | 2023-04-24 |  |  |  |  | 2023-05-01 |  |  |  |  | 2023-05-08 |  |  |  |  | 2023-05-15 |  |  |  |  | 2023-05-22 |  |  |  |  | 2023-05-29 |  |  |  |  | 2023-06-05 |  |  |  |  | 2023-06-12 |  |  |  |  | 2023-06-19 |  |  |  |  | 2023-06-26 |  |  |  |  | 2023-07-03 |  |  |  |  | 2023-07-10 |  |  |  |  | 2023-07-17 |  |  |  |  | 2023-07-24 |  |  |  |  | 2023-07-31 |  |  |  |  | 2023-08-07 |  |  |  |  | 2023-08-14 |  |  |  |  | 2023-08-21 |  |  |  |  | 2023-08-28 |  |  |  |  | 2023-09-04 |  |  |  |  | 2023-09-11 |  |  |  |  | 2023-09-18 |  |  |  |  | 2023-09-25 |  |  |  |  | 2023-10-02 |  |  |  |  | 2023-10-09 |  |  |  |  | 2023-10-16 |  |  |  |  | 2023-10-23 |  |  |  |  | 2023-10-30 |  |  |  |  | 2023-11-06 |  |  |  |  | 2023-11-13 |  |  |  |  | 2023-11-20 |  |  |  |  | 2023-11-27 |  |  |  |  | 2023-12-04 |  |  |  |  | 2023-12-11 | 2023-12-12 | 2023-12-13 | 2023-12-14 | 2023-12-15 | 2023-12-18 | 2023-12-19 | 2023-12-20 | 2023-12-21 | 2023-12-22 | 2023-12-25 | 2023-12-26 | 2023-12-27 | 2023-12-28 | 2023-12-29
|  |  | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F
|  | PRE-CON MEETINGS | [259 empty] | South Exterioirs EIFS
[252 empty] | Level 2 Zone E&F Framing | [9 empty] | Level 3 Fire Sprinkler |  |  |  |  | Level 3 OH MEP
|  | MILESTONES | [313 empty] | Air On
[14 empty] | Notice to Proceed | [64 empty] | Sitework Complete | [58 empty] | Foundation Complete | [84 empty] | Structure complete | [70 empty] | Power On | [14 empty] | Exterior Complete | [65 empty] | Interior Complete | [33 empty] | Substantial Completion | [19 empty] | Final Completion + Financial Completion
|  | PROCUREMENT | [140 empty] | Electrical Gear | [114 empty] | SES Fit-out & Energize
HVAC Equipment
Windows
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
BEGINNING SITEWORK WORK | [12 empty] | MOBILIZATION | [69 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
1H | Excavation/Grading | [16 empty] | 1H | 1H | 1H | 1H | 1H | 1H | 1H | 1H | 1H | 1H | 1H | 1H | 1H | 1H | 1H | 1I | 1I | 1I | 1I | 1I | 1I | 1I | 1I | 1I | 1I | 1I | 1I | 1I | 1I | 1I | 1I | 1I | 1I | 1I | 1I | 1J | 1J | 1J | 1J | 1J | 1J | 1J | 1J | 1J | 1J | 1J | 1J | 1J | 1J | 1J | 1J | 1J | 1J | 1J | 1J | 1K | 1K | 1K | 1K | 1K | B | B | B | B | B | B | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
1I | Install Storm/Sanitary/Water/Dry U.G. Utilities | [81 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
1J | Parking Area Base Stone | [81 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
1K | Final Grading | [81 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [34 empty] | Shaft Prep | [29 empty] | Elevator Cabs | [29 empty] | Certification | [13 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H |  |  |  |  | Comeback Areas for Elev | [20 empty] | H | [44 empty] | H
[82 empty] | ZONE A | H | F1 | F1 | F1 | F1 | F1 | F1 | F1 | F1 | F1 | F1 | F2 | F2 | F2 | F2 | F2 | F2 | F2 | F2 | F2 | F2 | F3 | F3 | F3 | F3 | H | F3 | F3 | F3 | F3 | F3 | F3 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | [25 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
FOUNDATION LEGEND | [82 empty] | H | [9 empty] | ZONE B | F1 | F1 | F1 | F1 | F1 | F1 | F1 | F1 | F1 | F1 | F2 | F2 | F2 | F2 | H | F2 | F2 | F2 | F2 | F2 | F2 | F3 | F3 | F3 | F3 | F3 | F3 | F3 | F3 | F3 | F3 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | B | B | B | [12 empty] | H | [53 empty] | H | H | H | H | [9 empty] | Erect Stair 1 | [10 empty] | H | H | [9 empty] | Erect Stair 2 | [98 empty] | H | [25 empty] | H | [44 empty] | H
F1 | Excavate & Pour Footings | [81 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [9 empty] | Pour 1 | [19 empty] | Pour 2 | [78 empty] | H | [25 empty] | H | [44 empty] | H
F2 | Columns & Walls | [81 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
F3 | UG MEP | [81 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
F4 | SOG | [81 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
B | Buffer | [81 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [28 empty] | LEVEL 1A | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S2 | S2 | H | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S3 | S3 | S3 | S3 | S3 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | [30 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [33 empty] | LEVEL 1B | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | H | S1 | S1 | S1 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S3 | S3 | S3 | S3 | S3 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | [25 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [38 empty] | LEVEL 2A | S1 | S1 | S1 | S1 | S1 | S1 | S1 | H | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S3 | S3 | S3 | S3 | S3 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | [20 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [43 empty] | LEVEL 2B | S1 | S1 | H | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S3 | S3 | S3 | S3 | S3 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | [15 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H |  |  | LEVEL 3A | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S3 | S3 | S3 | S3 | S3 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | [10 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
STRUCTURE LEGEND | [82 empty] | H | [24 empty] | H | [46 empty] | H | [7 empty] | LEVEL 3B | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S3 | S3 | S3 | S3 | S3 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | [5 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
S1 | Deck Formwork | [81 empty] | H | [24 empty] | H | [46 empty] | H | [12 empty] | LEVEL 4A | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S3 | S3 | S3 | S3 | S3 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
S2 | Deck MEP & Reinforcing | [81 empty] | H | [24 empty] | H | [46 empty] | H | [17 empty] | LEVEL 4B | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S3 | S3 | S3 | S3 | S3 | S4 | S4 | S4 | S4 | S4 | H | H | H | H | S4 | S4 | S4 | S4 | S4 | [15 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
S3 | Deck Inspections & Place | [10 empty] | Notice to Proceed | [70 empty] | H | [24 empty] | H | [46 empty] | H | [22 empty] | LEVEL 5A | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S3 | S3 | S3 | S3 | S3 | H | H | H | H | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | [10 empty] | H | H | [108 empty] | H | [25 empty] | H | [37 empty] | Substantial Completion | [6 empty] | H | [12 empty] | Final Completion + Financial Completion
S4 | Columns & Walls | [81 empty] | H | [24 empty] | H | [46 empty] | H | [27 empty] | LEVEL 5B | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | H | H | H | H | S3 | S3 | S3 | S3 | S3 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | B | B | B | B | B | B | B | B | B | B | B | B | [103 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H |  |  |  |  | ZONE 1A | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | B | B | B | 14 | 14 | 14 | 15 | 15 | 15 | [49 empty] | H | [25 empty] | H | [44 empty] | H
INTERIOR LEGEND | [82 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [7 empty] | ZONE 1B | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | B | B | B | 14 | 14 | 14 | 15 | 15 | 15 | [46 empty] | H | [25 empty] | H | [44 empty] | H
1 | Remove Reshores, Floor Prep & Wall Layout | [81 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [10 empty] | ZONE 1C | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | B | B | B | 14 | 14 | 14 | 15 | 15 | 15 | [43 empty] | H | [25 empty] | H | [44 empty] | H
2 | Fire Sprinkler & Install Walls | [81 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
3 | OH Mechanical Duct | [81 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
4 | OH Mech Equip, Piping, Branch Lines & Plumbing | [81 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [13 empty] | ZONE 2A | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | B | B | B | 14 | 14 | 14 | 15 | 15 | 15 | [40 empty] | H | [25 empty] | H | [44 empty] | H
5 | OH Electrical & Frame Walls | [81 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [16 empty] | ZONE 2B | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | B | B | B | 14 | 14 | 14 | 15 | 15 | 15 | [37 empty] | H | [25 empty] | H | [44 empty] | H
6 | Frame Walls, Install In-wall Electrical & Plumbing | [81 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [19 empty] | ZONE 2C | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | B | B | B | 14 | 14 | 14 | 15 | 15 | 15 | [34 empty] | H | [25 empty] | H | [44 empty] | H
7 | In-wall Process Piping, 1st Drywall, Insulation & Insp | [81 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [22 empty] | ZONE 2D | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | B | B | B | 14 | 14 | 14 | 15 | 15 | 15 | [31 empty] | H | [25 empty] | H | [44 empty] | H
8 | Finish Walls & Painting | [81 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [25 empty] | ZONE 2E | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | B | B | B | 14 | 14 | 14 | 15 | 15 | 15 | [28 empty] | H | [25 empty] | H | [44 empty] | H
9 | Painting & Install Ceiling Grid | [81 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [28 empty] | ZONE 2F | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | B | B | B | 14 | 14 | 14 | 15 | 15 | 15 | [25 empty] | H | [25 empty] | H | [44 empty] | H
10 | Install Electrical Fixtures & Mech Ceiling Drops | [81 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [31 empty] | ZONE 2G | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | B | B | B | 14 | 14 | 14 | 15 | 15 | 15 | [22 empty] | H | [25 empty] | H | [44 empty] | H
11 | Remaining Ceiling Drops & Install Casework | [81 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [34 empty] | ZONE 2H | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | B | B | B | 14 | 14 | 14 | 15 | 15 | 15 | [19 empty] | H | [25 empty] | H | [44 empty] | H
12 | Countertops, Millwork & Final Paint | [81 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [37 empty] | ZONE 2I | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | B | B | B | 14 | 14 | 14 | 15 | 15 | 15 | [16 empty] | H | [25 empty] | H | [44 empty] | H
13 | Wall & Casework Fixtures, Ceiling Tiles & Flooring | [81 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [40 empty] | ZONE 2J | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | B | B | B | 14 | 14 | 14 | 15 | 15 | 15 | [13 empty] | H | [25 empty] | H | [44 empty] | H
14 | Flooring, Final Paint & 1st Clean | [81 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [43 empty] | ZONE 2K | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | B | B | B | 14 | 14 | 14 | 15 | 15 | 15 | [10 empty] | H | [25 empty] | H | [44 empty] | H
15 | Punchlist, Corrections & Final Clean | [81 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [46 empty] | ZONE 3A | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | B | B | B | 14 | 14 | 14 | 15 | 15 | 15 | [7 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [49 empty] | ZONE 3B | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | B | B | B | 14 | 14 | 14 | 15 | 15 | 15 |  |  |  |  | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [52 empty] | ZONE 3C | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | B | B | B | 14 | 14 | 14 | 15 | 15 | 15 |  | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [55 empty] | ZONE 3D | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | B | B | B | 14 | 14 | 14 | 15 | H | 15 | 15 | [23 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [58 empty] | ZONE 3E | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | B | B | B | 14 | H | 14 | 14 | 15 | 15 | 15 | [20 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [61 empty] | ZONE 4A | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | B | H | B | B | 14 | 14 | 14 | 15 | 15 | 15 | [17 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [64 empty] | ZONE 4B | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | H | 13 | 13 | B | B | B | 14 | 14 | 14 | 15 | 15 | 15 | [14 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [67 empty] | ZONE 4C | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | H | 12 | 12 | 13 | 13 | 13 | B | B | B | 14 | 14 | 14 | 15 | 15 | 15 | [11 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [70 empty] | ZONE 4D | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | H | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | B | B | B | 14 | 14 | 14 | 15 | 15 | 15 | [8 empty] | H | [44 empty] | H
EXTERIOR LEGEND | [82 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [73 empty] | ZONE 4E | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | H | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | B | B | B | 14 | 14 | 14 | 15 | 15 | 15 | [5 empty] | H | [44 empty] | H
A | Structural Steel Supports | [81 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [76 empty] | ZONE 4F | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | H | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | B | B | B | 14 | 14 | 14 | 15 | 15 | 15 |  |  | H | [44 empty] | H
B | Framing & Sheathing | [81 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [79 empty] | ZONE 4G | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | H | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | B | B | B | 14 | 14 | 14 | 15 | 15 | H | 15 | [43 empty] | H
C | EIFS | [81 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [82 empty] | ZONE 4H | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | H | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | B | B | B | 14 | 14 | H | 14 | 15 | 15 | 15 | [40 empty] | H
D | Window Installation | [81 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [85 empty] | ZONE 4I | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | H | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | B | B | H | B | 14 | 14 | 14 | 15 | 15 | 15 | [37 empty] | H
E | Final Caulking & Finishes | [81 empty] | H | [24 empty] | H | [46 empty] | H | [47 empty] | WEST A | A | A | A | A | A | H | H | H | H | B | B | B | B | B | B | B | B | B | B | C | C | C | C | C | D | D | D | D | D | H | H | E | E | E | E | E | [103 empty] | H | [25 empty] | H | [44 empty] | H
F | Shade Structure | [81 empty] | H | [24 empty] | H | [46 empty] | H | [52 empty] | WEST B | H | H | H | H | A | A | A | A | A | B | B | B | B | B | B | B | B | B | B | C | C | C | C | C | H | H | D | D | D | D | D | E | E | E | E | E | [98 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H |  |  |  |  | WEST C | A | A | A | A | A | B | B | B | B | B | B | B | B | B | B | H | H | C | C | C | C | C | D | D | D | D | D | E | E | E | E | E | [73 empty] | ZONE 5A | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | H | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | H | 13 | B | B | B | 14 | 14 | 14 | 15 | 15 | 15 | [34 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [9 empty] | WEST D | A | A | A | A | A | B | B | B | B | B | H | H | B | B | B | B | B | C | C | C | C | C | D | D | D | D | D | E | E | E | E | E | [71 empty] | ZONE 5B | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | H | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | H | 12 | 13 | 13 | 13 | B | B | B | 14 | 14 | 14 | 15 | 15 | 15 | B | B | B | [28 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [14 empty] | EAST A | A | A | A | A | A | H | H | B | B | B | B | B | B | B | B | B | B | C | C | C | C | C | D | D | D | D | D | E | E | E | E | E | [83 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [19 empty] | EAST B | H | H | A | A | A | A | A | B | B | B | B | B | B | B | B | B | B | C | C | C | C | C | D | D | D | D | D | E | E | E | E | E | [78 empty] | H | [25 empty] | H | [44 empty] | H
FINISHING SITEWORK LEGEND | [82 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H |  |  |  |  | EAST C | A | A | A | A | A | B | B | B | B | B | B | B | B | B | B | C | C | C | C | C | D | D | D | D | D | E | E | E | E | E | [73 empty] | H | [25 empty] | H | [44 empty] | H
1 | Site Demoblization | [81 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [9 empty] | EAST D | A | A | A | A | A | B | B | B | B | B | B | B | B | B | B | C | C | C | C | C | D | D | D | D | D | E | E | E | E | E | [68 empty] | H | [25 empty] | H | [44 empty] | H
2 | UG Electrical | [81 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [14 empty] | NORTH A | A | A | A | A | A | B | B | B | B | B | B | B | B | B | B | C | C | C | C | C | D | D | D | D | D | E | E | E | E | E | [63 empty] | H | [25 empty] | H | [44 empty] | H
3 | Rough Grading | [81 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [19 empty] | NORTH B | A | A | A | A | A | B | B | B | B | B | B | B | B | B | B | C | C | C | C | C | D | D | D | D | D | E | E | E | E | E | [58 empty] | H | [25 empty] | H | [44 empty] | H
4 | Hardscaping | [81 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [24 empty] | NORTH C | A | A | A | A | A | B | B | B | B | B | B | B | B | B | B | C | C | C | C | C | D | D | D | D | D | E | E | E | E | E | [53 empty] | H | [25 empty] | H | [44 empty] | H
5 | Trees & Irrigation | [81 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [29 empty] | NORTH D | A | A | A | A | A | B | B | B | B | B | B | B | B | B | B | C | C | C | C | C | D | D | D | D | D | E | E | E | E | E | [48 empty] | H | [25 empty] | H | [44 empty] | H
6 | Landscaping | [81 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [34 empty] | SOUTH A | A | A | A | A | A | B | B | B | B | B | B | B | B | B | B | C | C | C | C | C | D | D | D | D | D | E | E | E | E | E | [43 empty] | H | [25 empty] | H | [44 empty] | H
7 | Paving | [81 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [39 empty] | SOUTH B | A | A | A | A | A | B | B | B | B | B | B | B | B | B | B | C | C | C | C | C | D | D | D | D | D | E | E | E | E | E | [38 empty] | H | [25 empty] | H | [44 empty] | H
8 | Site Finishes | [81 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [44 empty] | SOUTH C | A | A | A | A | A | B | B | B | B | B | B | B | B | B | B | C | C | C | C | C | D | D | D | D | D | E | E | E | E | E | [33 empty] | H | [13 empty] | Pre-functional Checklists | [11 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [49 empty] | SOUTH D | A | A | A | A | A | B | B | B | B | B | B | B | B | B | B | C | C | C | C | C | D | D | D | D | D | E | E | E | E | E | [28 empty] | H | [24 empty] | Controls | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [14 empty] | TAB | [29 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [23 empty] | Cx + FA Testing | [10 empty] | B | B | B | B | [6 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [23 empty] | LS/ FA Testing | [20 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [33 empty] | Functional Performance Testing | [10 empty] | H | [9 empty] | B | B | B | B
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [80 empty] | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F |  |  |  | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [58 empty] | Roofing Area A | [49 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [73 empty] | Roofing Area B | [34 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [104 empty] | AREA A | 1 | 1 | 1 | H | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | H | 7 | 7 | 8 | 8 | 8 | 8 | 8 | [37 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H |  | AREA B | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | H | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | [32 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [6 empty] | AREA C | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | H | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | B | B | B | B | B | B | B | B | B | B | B | B | B | B | B | B | B | B | B | B | B | [6 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [79 empty] | Set AHU | [28 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [89 empty] | Mechanical Installation | [18 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [99 empty] | Controls | [8 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H |  | Point to Point | [23 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [6 empty] | Mech Startup | [18 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
Interiors Phase
Exteriors Phase
Structure Phase
Foundations Phase
Sitework Phase
6 Week Look Ahead
Neuroscience Institute Takt Plan
WWP
Zone Map
POWER ON
AIR ON

## Activity Durations
Type in your # of zones and it will automatically calculate the columns based on the duration per floor: |  |  |  | # of Zones: | 8
Activity List: | Duration per Floor: | No. of Zones | Crew Count: | Duration per Zone: | Duration / Zone (Days)
Remove re-shores | 5 | 8 | 4 | 0.625 | 1
Final patch ceiling | 10 | 8 | 3 | 1.25 | 2
Sweep floor | 3 | 8 | 2 | 0.375 | 1
Refresh control lines | 3 | 8 | 3 | 0.375 | 1
Layout walls | 5 | 8 | 3 | 0.625 | 1
Install fire sprinkler main and branch lines | 15 | 8 | 4 | 1.875 | 2
Install priority walls including elec and comm rooms | 9 | 8 | 6 | 1.125 | 2
Install overhead mechanical duct | 25 | 8 | 8 | 3.125 | 4
Install overhead mechanical equipment | 10 | 8 | 4 | 1.25 | 2
Install overhead mechanical piping | 10 | 8 | 4 | 1.25 | 2
Install overhead mechanical branch lines | 10 | 8 | 4 | 1.25 | 2
Install overhead plumbing | 9 | 8 | 6 | 1.125 | 2
Install overhead electrical | 15 | 8 | 7 | 1.875 | 2
Frame all walls | 15 | 8 | 6 | 1.875 | 2
Install in-wall electrical | 15 | 8 | 6 | 1.875 | 2
Install in-wall plumbing | 15 | 8 | 4 | 1.875 | 2
Install in-wall process piping | 8 | 8 | 2 | 1 | 1
One-side drywall | 12 | 8 | 5 | 1.5 | 2
In-wall inspections | 5 | 8 | 1 | 0.625 | 1
Place insulation | 5 | 8 | 2 | 0.625 | 1
Second side drywall | 12 | 8 | 5 | 1.5 | 2
Tape, bed, and finish walls | 12 | 8 | 9 | 1.5 | 2
Prime, 1st & 2nd coat paint | 15 | 8 | 5 | 1.875 | 2
Install ceiling grid | 15 | 8 | 3 | 1.875 | 2
Install lights and electrical fixtures | 20 | 8 | 6 | 2.5 | 3
Install mechanical ceiling drops | 5 | 8 | 2 | 0.625 | 1
All remaining ceiling drops | 5 | 8 | 2 | 0.625 | 1
Install casework | 20 | 8 | 4 | 2.5 | 3
Install countertops | 9 | 8 | 3 | 1.125 | 2
Millwork plumbing fixture install | 6 | 8 | 2 | 0.75 | 1
Final paint (possible) | 7 | 8 | 3 | 0.875 | 1
Install wall and casework fixtures | 7 | 8 | 3 | 0.875 | 1
Place ceiling tiles | 4 | 8 | 1 | 0.5 | 1
Install flooring | 15 | 8 | 4 | 1.875 | 2
Final paint | 6 | 8 | 2 | 0.75 | 1
Final clean first pass | 5 | 8 | 3 | 0.625 | 1
Incomplete work list | 10 | 8 | 2 | 1.25 | 2
Architect punchlist | 10 | 8 | 2 | 1.25 | 2
Corrections | 10 | 8 | 4 | 1.25 | 2
Final clean | 5 | 8 | 3 | 0.625 | 1

## Calculator
|  |  | Takt Wagons | Takt Zones | Takt Time Unrounded | Theoretical Low Limit | Train Length | Takt Time | Duration | Trade Time Gained | Area per Zone | Takt Level | Realized Flow Potential | Efficiency Parametric | Value Parametric | 4 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200
[17 empty] | 1 | 1: 1; 2: 1; 3: 1; 4: 1; 5: 1; 6: 2; 7: 2; 8: 2; 9: 2; 10: 2; 11: 3; 12: 3; 13: 3; 14: 3; 15: 3; 16: 4; 17: 4; 18: 4; 19: 4; 20: 4; 21: 5; 22: 5; 23: 5; 24: 5; 25: 5; 26: 6; 27: 6; 28: 6; 29: 6; 30: 6; 31: 7; 32: 7; 33: 7; 34: 7; 35: 7; 36: 8; 37: 8; 38: 8; 39: 8; 40: 8; 41: 9; 42: 9; 43: 9; 44: 9; 45: 9; 46: 10; 47: 10; 48: 10; 49: 10; 50: 10; 51: 11; 52: 11; 53: 11; 54: 11; 55: 11; 56: 12; 57: 12; 58: 12; 59: 12; 60: 12; 61: 13; 62: 13; 63: 13; 64: 13; 65: 13; 66: 14; 67: 14; 68: 14; 69: 14; 70: 14; 71: 15; 72: 15; 73: 15; 74: 15; 75: 15
|  |  | 15 | 2 | 12.5 | 200 | 195 | 13 | 208 | 1 | 24712.5 | Bad | 18.75% | 7.5 | 15 |  | 2 | 6: 1; 7: 1; 8: 1; 9: 1; 10: 1; 11: 2; 12: 2; 13: 2; 14: 2; 15: 2; 16: 3; 17: 3; 18: 3; 19: 3; 20: 3; 21: 4; 22: 4; 23: 4; 24: 4; 25: 4; 26: 5; 27: 5; 28: 5; 29: 5; 30: 5; 31: 6; 32: 6; 33: 6; 34: 6; 35: 6; 36: 7; 37: 7; 38: 7; 39: 7; 40: 7; 41: 8; 42: 8; 43: 8; 44: 8; 45: 8; 46: 9; 47: 9; 48: 9; 49: 9; 50: 9; 51: 10; 52: 10; 53: 10; 54: 10; 55: 10; 56: 11; 57: 11; 58: 11; 59: 11; 60: 11; 61: 12; 62: 12; 63: 12; 64: 12; 65: 12; 66: 13; 67: 13; 68: 13; 69: 13; 70: 13; 71: 14; 72: 14; 73: 14; 74: 14; 75: 14; 76: 15; 77: 15; 78: 15; 79: 15; 80: 15
|  |  | 15 | 3 | 8.3333 | 141.6667 | 135 | 9 | 153 | 2 | 16475 | Bad | 25.49% | 5 | 7.5 |  | 3 | 11: 1; 12: 1; 13: 1; 14: 1; 15: 1; 16: 2; 17: 2; 18: 2; 19: 2; 20: 2; 21: 3; 22: 3; 23: 3; 24: 3; 25: 3; 26: 4; 27: 4; 28: 4; 29: 4; 30: 4; 31: 5; 32: 5; 33: 5; 34: 5; 35: 5; 36: 6; 37: 6; 38: 6; 39: 6; 40: 6; 41: 7; 42: 7; 43: 7; 44: 7; 45: 7; 46: 8; 47: 8; 48: 8; 49: 8; 50: 8; 51: 9; 52: 9; 53: 9; 54: 9; 55: 9; 56: 10; 57: 10; 58: 10; 59: 10; 60: 10; 61: 11; 62: 11; 63: 11; 64: 11; 65: 11; 66: 12; 67: 12; 68: 12; 69: 12; 70: 12; 71: 13; 72: 13; 73: 13; 74: 13; 75: 13; 76: 14; 77: 14; 78: 14; 79: 14; 80: 14; 81: 15; 82: 15; 83: 15; 84: 15; 85: 15
|  |  | 15 | 4 | 6.25 | 112.5 | 105 | 7 | 126 | 3 | 12356.25 | Macro | 30.95% | 3.75 | 5 |  | 4 | 16: 1; 17: 1; 18: 1; 19: 1; 20: 1; 21: 2; 22: 2; 23: 2; 24: 2; 25: 2; 26: 3; 27: 3; 28: 3; 29: 3; 30: 3; 31: 4; 32: 4; 33: 4; 34: 4; 35: 4; 36: 5; 37: 5; 38: 5; 39: 5; 40: 5; 41: 6; 42: 6; 43: 6; 44: 6; 45: 6; 46: 7; 47: 7; 48: 7; 49: 7; 50: 7; 51: 8; 52: 8; 53: 8; 54: 8; 55: 8; 56: 9; 57: 9; 58: 9; 59: 9; 60: 9; 61: 10; 62: 10; 63: 10; 64: 10; 65: 10; 66: 11; 67: 11; 68: 11; 69: 11; 70: 11; 71: 12; 72: 12; 73: 12; 74: 12; 75: 12; 76: 13; 77: 13; 78: 13; 79: 13; 80: 13; 81: 14; 82: 14; 83: 14; 84: 14; 85: 14; 86: 15; 87: 15; 88: 15; 89: 15; 90: 15
Takt Inputs |  |  | 15 | 5 | 5 | 95 | 75 | 5 | 95 | 0 | 9885 | Macro | 41.05% | 3 | 3.75 | x | 5 | 21: 1; 22: 1; 23: 1; 24: 1; 25: 1; 26: 2; 27: 2; 28: 2; 29: 2; 30: 2; 31: 3; 32: 3; 33: 3; 34: 3; 35: 3; 36: 4; 37: 4; 38: 4; 39: 4; 40: 4; 41: 5; 42: 5; 43: 5; 44: 5; 45: 5; 46: 6; 47: 6; 48: 6; 49: 6; 50: 6; 51: 7; 52: 7; 53: 7; 54: 7; 55: 7; 56: 8; 57: 8; 58: 8; 59: 8; 60: 8; 61: 9; 62: 9; 63: 9; 64: 9; 65: 9; 66: 10; 67: 10; 68: 10; 69: 10; 70: 10; 71: 11; 72: 11; 73: 11; 74: 11; 75: 11; 76: 12; 77: 12; 78: 12; 79: 12; 80: 12; 81: 13; 82: 13; 83: 13; 84: 13; 85: 13; 86: 14; 87: 14; 88: 14; 89: 14; 90: 14; 91: 15; 92: 15; 93: 15; 94: 15; 95: 15
|  |  | 15 | 6 | 4.1667 | 83.3333 | 75 | 5 | 100 | 5 | 8237.5 | Macro | 39% | 2.5 | 3 |  | 6
Takt Wagons |  | 15 | 15 | 7 | 3.5714 | 75 | 60 | 4 | 84 | 3 | 7060.7143 | Macro | 46.43% | 2.1429 | 2.5 |  | 7
|  |  | 15 | 8 | 3.125 | 68.75 | 60 | 4 | 88 | 7 | 6178.125 | Macro | 44.32% | 1.875 | 2.1429 |  | 8
Takt Zones |  | 5 | 15 | 9 | 2.7778 | 63.8889 | 45 | 3 | 69 | 2 | 5491.6667 | Norm | 56.52% | 1.6667 | 1.875 |  | 9
|  |  | 15 | 10 | 2.5 | 60 | 45 | 3 | 72 | 5 | 4942.5 | Norm | 54.17% | 1.5 | 1.6667 |  | 10
Takt Time |  | 5 | 15 | 11 | 2.2727 | 56.8182 | 45 | 3 | 75 | 8 | 4493.1818 | Norm | 52% | 1.3636 | 1.5 |  | 11
|  |  | 15 | 12 | 2.0833 | 54.1667 | 45 | 3 | 78 | 11 | 4118.75 | Norm | 50% | 1.25 | 1.3636 |  | 12
Duration |  | 95 | 15 | 13 | 1.9231 | 51.9231 | 30 | 2 | 54 | 1 | 3801.9231 | Norm | 72.22% | 1.1538 | 1.25 |  | 13
|  |  | 15 | 14 | 1.7857 | 50 | 30 | 2 | 56 | 3 | 3530.3571 | Norm | 69.64% | 1.0714 | 1.1538 |  | 14
Area Inputs (m2, sqft) |  |  | 15 | 15 | 1.6667 | 48.3333 | 30 | 2 | 58 | 5 | 3295 | Norm | 67.24% | 1 | 1.0714 |  | 15
|  |  | 15 | 16 | 1.5625 | 46.875 | 30 | 2 | 60 | 7 | 3089.0625 | Norm | 65% | 0.9375 | 1 |  | 16
Area / Zone |  | 9885 | 15 | 17 | 1.4706 | 45.5882 | 30 | 2 | 62 | 9 | 2907.3529 | Norm | 62.9% | 0.88235 | 0.9375 |  | 17
|  |  | 15 | 18 | 1.3889 | 44.4444 | 30 | 2 | 64 | 11 | 2745.8333 | Norm | 60.94% | 0.83333 | 0.88235 |  | 18
Min Zone Size |  | 1000 | 15 | 19 | 1.3158 | 43.4211 | 30 | 2 | 66 | 13 | 2601.3158 | Norm | 59.09% | 0.78947 | 0.83333 |  | 19
|  |  | 15 | 20 | 1.25 | 42.5 | 30 | 2 | 68 | 15 | 2471.25 | Norm | 57.35% | 0.75 | 0.78947 |  | 20
Max Zone Size |  | 10000 | 15 | 21 | 1.1905 | 41.6667 | 30 | 2 | 70 | 17 | 2353.5714 | Norm | 55.71% | 0.71429 | 0.75 |  | 21
|  |  | 15 | 22 | 1.1364 | 40.9091 | 30 | 2 | 72 | 19 | 2246.5909 | Norm | 54.17% | 0.68182 | 0.71429 |  | 22
Total SQFT of Phase |  | 49425 | 15 | 23 | 1.087 | 40.2174 | 30 | 2 | 74 | 21 | 2148.913 | Norm | 52.7% | 0.65217 | 0.68182 |  | 23
|  |  | 15 | 24 | 1.0417 | 39.5833 | 30 | 2 | 76 | 23 | 2059.375 | Norm | 51.32% | 0.625 | 0.65217 |  | 24
Shortest Durations |  |  | 15 | 25 | 1 | 39 | 15 | 1 | 39 | 0 | 1977 | Norm | 100% | 0.6 | 0.625 |  | 25
|  |  | 15 | 26 | 0.96154 | 38.4615 | 15 | 1 | 40 | 1 | 1900.9615 | Norm | 97.5% | 0.57692 | 0.6 |  | 26
Best # Zones | Takt Time | Duration | 15 | 27 | 0.92593 | 37.963 | 15 | 1 | 41 | 2 | 1830.5556 | Norm | 95.12% | 0.55556 | 0.57692 |  | 27
25 | 1 | 39 | 15 | 28 | 0.89286 | 37.5 | 15 | 1 | 42 | 3 | 1765.1786 | Norm | 92.86% | 0.53571 | 0.55556 |  | 28
13 | 2 | 54 | 15 | 29 | 0.86207 | 37.069 | 15 | 1 | 43 | 4 | 1704.3103 | Norm | 90.7% | 0.51724 | 0.53571 |  | 29
9 | 3 | 69 | 15 | 30 | 0.83333 | 36.6667 | 15 | 1 | 44 | 5 | 1647.5 | Norm | 88.64% | 0.5 | 0.51724 |  | 30
7 | 4 | 84 | 15 | 31 | 0.80645 | 36.2903 | 15 | 1 | 45 | 6 | 1594.3548 | Norm | 86.67% | 0.48387 | 0.5 |  | 31
5 | 5 | 95 | 15 | 32 | 0.78125 | 35.9375 | 15 | 1 | 46 | 7 | 1544.5312 | Norm | 84.78% | 0.46875 | 0.48387 |  | 32
5 | 6 | 114 | 15 | 33 | 0.75758 | 35.6061 | 15 | 1 | 47 | 8 | 1497.7273 | Norm | 82.98% | 0.45455 | 0.46875 |  | 33
4 | 7 | 126 | 15 | 34 | 0.73529 | 35.2941 | 15 | 1 | 48 | 9 | 1453.6765 | Norm | 81.25% | 0.44118 | 0.45455 |  | 34
4 | 8 | 144 | 15 | 35 | 0.71429 | 35 | 15 | 1 | 49 | 10 | 1412.1429 | Norm | 79.59% | 0.42857 | 0.44118 |  | 35
3 | 9 | 153 | 15 | 36 | 0.69444 | 34.7222 | 15 | 1 | 50 | 11 | 1372.9167 | Norm | 78% | 0.41667 | 0.42857 |  | 36
3 | 10 | 170 | 15 | 37 | 0.67568 | 34.4595 | 15 | 1 | 51 | 12 | 1335.8108 | Norm | 76.47% | 0.40541 | 0.41667 |  | 37
[17 empty] | 38 | 1: Wagons; 5: 15
[17 empty] | 39 | 1: Zones; 5: 5; 7: .; 8: .; 9: .; 10: .; 11: .
[17 empty] | 40 | 1: Takt Time; 5: 5; 7: .; 8: .; 9: .; 10: .; 11: .
[18 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200
[17 empty] | 1 | Takt Time 1: 1; Takt Time 2: 1; Takt Time 3: 1; Takt Time 4: 1; 5 5: 1; 5 6: 2; . 7: 2; . 8: 2; . 9: 2; . 10: 2; . 11: 3; . 12: 3; . 13: 3; . 14: 3; . 15: 3; . 16: 4; . 17: 4; . 18: 4; . 19: 4; . 20: 4; . 21: 5; . 22: 5; . 23: 5; . 24: 5; . 25: 5; . 26: 6; . 27: 6; . 28: 6; . 29: 6; . 30: 6; . 31: 7; . 32: 7; . 33: 7; . 34: 7; . 35: 7; . 36: 8; . 37: 8; . 38: 8; . 39: 8; . 40: 8; . 41: 9; . 42: 9; . 43: 9; . 44: 9; . 45: 9; . 46: 10; . 47: 10; . 48: 10; . 49: 10; . 50: 10; . 51: 11; . 52: 11; . 53: 11; . 54: 11; . 55: 11; . 56: 12; . 57: 12; . 58: 12; . 59: 12; . 60: 12; . 61: 13; . 62: 13; . 63: 13; . 64: 13; . 65: 13; . 66: 14; . 67: 14; . 68: 14; . 69: 14; . 70: 14; . 71: 15; . 72: 15; . 73: 15; . 74: 15; . 75: 15
[17 empty] | 2 | 5 6: 1; . 7: 1; . 8: 1; . 9: 1; . 10: 1; . 11: 2; . 12: 2; . 13: 2; . 14: 2; . 15: 2; . 16: 3; . 17: 3; . 18: 3; . 19: 3; . 20: 3; . 21: 4; . 22: 4; . 23: 4; . 24: 4; . 25: 4; . 26: 5; . 27: 5; . 28: 5; . 29: 5; . 30: 5; . 31: 6; . 32: 6; . 33: 6; . 34: 6; . 35: 6; . 36: 7; . 37: 7; . 38: 7; . 39: 7; . 40: 7; . 41: 8; . 42: 8; . 43: 8; . 44: 8; . 45: 8; . 46: 9; . 47: 9; . 48: 9; . 49: 9; . 50: 9; . 51: 10; . 52: 10; . 53: 10; . 54: 10; . 55: 10; . 56: 11; . 57: 11; . 58: 11; . 59: 11; . 60: 11; . 61: 12; . 62: 12; . 63: 12; . 64: 12; . 65: 12; . 66: 13; . 67: 13; . 68: 13; . 69: 13; . 70: 13; . 71: 14; . 72: 14; . 73: 14; . 74: 14; . 75: 14; . 76: 15; . 77: 15; . 78: 15; . 79: 15; . 80: 15
[17 empty] | 3 | . 11: 1; . 12: 1; . 13: 1; . 14: 1; . 15: 1; . 16: 2; . 17: 2; . 18: 2; . 19: 2; . 20: 2; . 21: 3; . 22: 3; . 23: 3; . 24: 3; . 25: 3; . 26: 4; . 27: 4; . 28: 4; . 29: 4; . 30: 4; . 31: 5; . 32: 5; . 33: 5; . 34: 5; . 35: 5; . 36: 6; . 37: 6; . 38: 6; . 39: 6; . 40: 6; . 41: 7; . 42: 7; . 43: 7; . 44: 7; . 45: 7; . 46: 8; . 47: 8; . 48: 8; . 49: 8; . 50: 8; . 51: 9; . 52: 9; . 53: 9; . 54: 9; . 55: 9; . 56: 10; . 57: 10; . 58: 10; . 59: 10; . 60: 10; . 61: 11; . 62: 11; . 63: 11; . 64: 11; . 65: 11; . 66: 12; . 67: 12; . 68: 12; . 69: 12; . 70: 12; . 71: 13; . 72: 13; . 73: 13; . 74: 13; . 75: 13; . 76: 14; . 77: 14; . 78: 14; . 79: 14; . 80: 14; . 81: 15; . 82: 15; . 83: 15; . 84: 15; . 85: 15
[17 empty] | 4 | . 16: 1; . 17: 1; . 18: 1; . 19: 1; . 20: 1; . 21: 2; . 22: 2; . 23: 2; . 24: 2; . 25: 2; . 26: 3; . 27: 3; . 28: 3; . 29: 3; . 30: 3; . 31: 4; . 32: 4; . 33: 4; . 34: 4; . 35: 4; . 36: 5; . 37: 5; . 38: 5; . 39: 5; . 40: 5; . 41: 6; . 42: 6; . 43: 6; . 44: 6; . 45: 6; . 46: 7; . 47: 7; . 48: 7; . 49: 7; . 50: 7; . 51: 8; . 52: 8; . 53: 8; . 54: 8; . 55: 8; . 56: 9; . 57: 9; . 58: 9; . 59: 9; . 60: 9; . 61: 10; . 62: 10; . 63: 10; . 64: 10; . 65: 10; . 66: 11; . 67: 11; . 68: 11; . 69: 11; . 70: 11; . 71: 12; . 72: 12; . 73: 12; . 74: 12; . 75: 12; . 76: 13; . 77: 13; . 78: 13; . 79: 13; . 80: 13; . 81: 14; . 82: 14; . 83: 14; . 84: 14; . 85: 14; . 86: 15; . 87: 15; . 88: 15; . 89: 15; . 90: 15
[17 empty] | 5 | . 21: 1; . 22: 1; . 23: 1; . 24: 1; . 25: 1; . 26: 2; . 27: 2; . 28: 2; . 29: 2; . 30: 2; . 31: 3; . 32: 3; . 33: 3; . 34: 3; . 35: 3; . 36: 4; . 37: 4; . 38: 4; . 39: 4; . 40: 4; . 41: 5; . 42: 5; . 43: 5; . 44: 5; . 45: 5; . 46: 6; . 47: 6; . 48: 6; . 49: 6; . 50: 6; . 51: 7; . 52: 7; . 53: 7; . 54: 7; . 55: 7; . 56: 8; . 57: 8; . 58: 8; . 59: 8; . 60: 8; . 61: 9; . 62: 9; . 63: 9; . 64: 9; . 65: 9; . 66: 10; . 67: 10; . 68: 10; . 69: 10; . 70: 10; . 71: 11; . 72: 11; . 73: 11; . 74: 11; . 75: 11; . 76: 12; . 77: 12; . 78: 12; . 79: 12; . 80: 12; . 81: 13; . 82: 13; . 83: 13; . 84: 13; . 85: 13; . 86: 14; . 87: 14; . 88: 14; . 89: 14; . 90: 14; . 91: 15; . 92: 15; . 93: 15; . 94: 15; . 95: 15
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
[17 empty] | 38 | Takt Time 1: Wagons; 5 5: 15
[17 empty] | 39 | Takt Time 1: Zones; 5 5: 5
[17 empty] | 40 | Takt Time 1: Takt Time; 5 5: 5
Optimize the
Takt Phase
Overflow Warning
Overflow Warning

## Work Density
Work Density Table
[35 empty] | Zone | Density
[35 empty] | 1 | 0
[35 empty] | 2 | 0
[35 empty] | 3 | 0
[35 empty] | 4 | 0
[35 empty] | 5 | 0
[35 empty] | 6 | 0
[35 empty] | 7 | 0
[35 empty] | 8 | 0
[35 empty] | 9 | 0
[35 empty] | 10 | 0
[35 empty] | 11 | 0
Creating & populating grid according to our scale
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
|  |  | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
|  |  | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
|  |  | 0 | 3 | 4 | 4 | 6 | 6 | 6 | 3 | 3 | 3
|  |  | 3 | 3 | 6 | 4 | 6 | 6 | 6 | 3 | 3 | 3 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
|  |  | 3 | 3 | 6 | 4 | 6 | 6 | 6 | 3 | 3 | 3 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
|  |  | 3 | 3 | 6 | 4 | 7 | 7 | 7 | 7 | 3 | 3 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
|  |  | 3 | 3 | 6 | 4 | 7 | 7 | 7 | 9 | 9 | 9 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
|  |  | 3 | 3 | 4 | 4 | 7 | 7 | 7 | 9 | 9 | 9 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 8 | 8 | 8 | 8 | 8 | 8
|  |  | 3 | 3 | 4 | 4 | 7 | 7 | 7 | 9 | 9 | 9 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 7 | 8 | 8 | 8 | 8 | 8
|  |  | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 9 | 9 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 7 | 7 | 7 | 7 | 8 | 8
|  |  | 2 | 8 | 8 | 8 | 4 | 4 | 4 | 4 | 8 | 8 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
|  |  | 2 | 8 | 8 | 8 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Work density with initial zoning (aggregate scores)
| Work Density Table | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| Zone | Density | [6 empty] | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| 1 | 84 | [6 empty] | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| 2 | 160 | [6 empty] | 0 | 3 | 4 | 4 | 6 | 6 | 6 | 3 | 3 | 3
| 3 | 159 | [6 empty] | 3 | 3 | 6 | 4 | 6 | 6 | 6 | 3 | 3 | 3 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| 4 | 103 | [6 empty] | 3 | 3 | 6 | 4 | 6 | 6 | 6 | 3 | 3 | 3 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| 5 | 108 | [6 empty] | 3 | 3 | 6 | 4 | 7 | 7 | 7 | 7 | 3 | 3 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| 6 | 160 | [6 empty] | 3 | 3 | 6 | 4 | 7 | 7 | 7 | 9 | 9 | 9 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| 7 | 160 | [6 empty] | 3 | 3 | 4 | 4 | 7 | 7 | 7 | 9 | 9 | 9 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 8 | 8 | 8 | 8 | 8 | 8
| 8 | 108 | [6 empty] | 3 | 3 | 4 | 4 | 7 | 7 | 7 | 9 | 9 | 9 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 7 | 8 | 8 | 8 | 8 | 8
| 9 | 202 | [6 empty] | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 9 | 9 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 7 | 7 | 7 | 7 | 8 | 8
| 10 | 201 | [6 empty] | 2 | 8 | 8 | 8 | 4 | 4 | 4 | 4 | 8 | 8 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 11 | 197 | [6 empty] | 2 | 8 | 8 | 8 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Adjusing areas for a better density leveling
| Work Density Table | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| Zone | Density | [5 empty] | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| 1 | 150 | [5 empty] | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| 2 | 152 | [5 empty] | 0 | 3 | 4 | 4 | 6 | 6 | 6 | 3 | 3 | 3
| 3 | 151 | [5 empty] | 3 | 3 | 6 | 4 | 6 | 6 | 6 | 3 | 3 | 3 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| 4 | 154 | [5 empty] | 3 | 3 | 6 | 4 | 6 | 6 | 6 | 3 | 3 | 3 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| 5 | 151 | [5 empty] | 3 | 3 | 6 | 4 | 7 | 7 | 7 | 7 | 3 | 3 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| 6 | 152 | [5 empty] | 3 | 3 | 6 | 4 | 7 | 7 | 7 | 9 | 9 | 9 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| 7 | 150 | [5 empty] | 3 | 3 | 4 | 4 | 7 | 7 | 7 | 9 | 9 | 9 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 8 | 8 | 8 | 8 | 8 | 8
| 8 | 151 | [5 empty] | 3 | 3 | 4 | 4 | 7 | 7 | 7 | 9 | 9 | 9 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 7 | 8 | 8 | 8 | 8 | 8
| 9 | 156 | [5 empty] | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 9 | 9 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 7 | 7 | 7 | 7 | 8 | 8
| 10 | 156 | [5 empty] | 2 | 8 | 8 | 8 | 4 | 4 | 4 | 4 | 8 | 8 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 11 | 157 | [5 empty] | 2 | 8 | 8 | 8 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Start Here
General process:
1. Study the drawings & understand the level of effor of each area
2. Create your scale and example. Make notes by column square on all drawings
3. Identify any one-off scopes of work that do not represent the average and note them
4. Aggregate your scores
5. Create work densities by column square
6. Adjust if needed
* Example scale for analyising Level of Effort for an interiors phase

## One Floor Macro Example
[16 empty] | 2022 | [38 empty] | 2023 | [34 empty] | 2024 | [52 empty] | 2025 | [51 empty] | 2026 | [51 empty] | 2027
[47 empty] | Cold Winter Months | [42 empty] | Cold Winter Months | [43 empty] | Cold Winter Months | [51 empty] | Cold Winter Months | [51 empty] | Cold Winter Months | [51 empty] | Cold Winter Months
[16 empty] | APRIL |  |  |  | MAY |  |  |  |  | JUNE |  |  |  | JULY |  |  |  | AUGUST |  |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  |  | NOVEMBER |  |  |  | DECEMBER |  |  |  | JANUARY |  |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  | MAY |  |  |  |  | JUNE |  |  |  | JULY |  |  |  |  | AUGUST |  |  |  | JANUARY |  |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  |  | MAY |  |  |  | JUNE |  |  |  | JULY |  |  |  |  | AUGUST |  |  |  | SEPTEMBER |  |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  | DECEMBER |  |  |  |  | JANUARY |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUGUST |  |  |  | SEPTEMBER |  |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  | DECEMBER |  |  |  |  | JANUARY |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUGUST |  |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  |  | DECEMBER |  |  |  | JANUARY |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  |  | JUNE |  |  |  | JULY |  |  |  | AUGUST |  |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  |  | DECEMBER
[16 empty] | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10 | 2023-07-17 | 2023-07-24 | 2023-07-31 | 2023-08-07 | 2023-08-14 | 2023-08-21 | 2023-08-28 | time axis 2024-01-01 to 2027-12-27
[34 empty] | # Weeks |  |  | Description |  |  |  | Long Lead Procurment
[36 empty] | 14 | Kitchens | [33 empty] | D | D | B
[16 empty] | 1 | Remove re-shores & Final patch ceiling | [18 empty] | 8 | Cabinets | [32 empty] | D | D | D
[16 empty] | 2 | Floor prep & Wall layout | [18 empty] | 20 | Light Fixtures | [32 empty] | D
[16 empty] | 3 | Sprinkler main and branch lines
[16 empty] | 4 | Priority walls & Install OH mecanical duct
[16 empty] | 5 | Install OH mechanical duct | [65 empty] | SUBSTANTIAL COMPLETION
[16 empty] | 6 | Install OH mechanical equipment & piping
[16 empty] | 7 | Install OH mechanical branch lines & OH plumbing | [37 empty] | Zone 1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
[16 empty] | 8 | OH electrical | [38 empty] | Zone 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
[16 empty] | 9 | Frame walls | [39 empty] | Zone 3 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
[16 empty] | 10 | In-wall electrical & Plumbing | [39 empty] | 15 14 13: Power on; 21 20 19: Air on
[16 empty] | 11 | In-wall process piping & One-side drywall
[16 empty] | 12 | In-wall inspections & Place insulation
[16 empty] | 13 | Finish walls
[16 empty] | 14 | Painting 1st & 2nd coat
[16 empty] | 15 | Ceiling grid
[16 empty] | 16 | Electrical fixtures
[16 empty] | 17 | Electrical fixtures, Install mech ceiling & remaining drops
[16 empty] | 18 | Casework
[16 empty] | 19 | Casework & Countertops
[16 empty] | 20 | Millwork & Final paint
[16 empty] | 21 | Wall and casework fixtures & Ceiling tiles
[16 empty] | 22 | Flooring
[16 empty] | 23 | Final paint & First Clean
[16 empty] | 24 | Worklist & Punchlist
[16 empty] | 25 | Corrections & Final clean
This steps are also processed in miro, you can find a template in the next link:
https://miro.com/app/board/uXjVOj11FK4=/?share_link_id=422339222032
Try to remain in the Macro Range from the middle to the bottom
[34 empty] | # Weeks |  |  | Description |  |  |  | Long Lead Procurment
[36 empty] | 14 | Kitchens | bar: 2 1 Zone 3 to 10 9 8
[36 empty] | 8 | Cabinets | bar: 2 1 Zone 3 to 9 8 7
[36 empty] | 20 | Light Fixtures | bar: 2 1 Zone 3 to 7 6 5
[55 empty] | JANUARY |  | 5 4 3: FEBRUARY; 9 8 7: MARCH; 13 12 11: APRIL; 17 16 15: MAY; 22 21 20: JUNE; 25 25 24: JULY
[35 empty] | 1 | Remove re-shores, Floor Prep & Wall Layout | [20 empty] | 20 19 18: SUBSTANTIAL COMPLETION | ORIGINAL SUBSTANTIAL COMPLETION
[35 empty] | 2 | Fire Sprinkler & Install Walls | [18 empty] | Zone 1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[35 empty] | 3 | OH Mechanical Duct | [19 empty] | Zone 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[35 empty] | 4 | OH Mech Equip, Piping, Branch Lines & Plumbing | [20 empty] | Zone 3 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[35 empty] | 5 | OH Electrical & Frame Walls | [21 empty] | Zone 4 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[35 empty] | 6 | Frame Walls, Install In-wall Electrical & Plumbing | [22 empty] | Zone 5 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[35 empty] | 7 | In-wall Process Piping, 1st Drywall, Insulation & Insp | [22 empty] | 7 6 5 4 3: Power on; 11 10 9 8 7: Air on
[35 empty] | 8 | Finish Walls & Painting
[35 empty] | 9 | Painting & Install Ceiling Grid
[35 empty] | 10 | Install Electrical Fixtures & Mech Ceiling Drops
[35 empty] | 11 | Remaining Ceiling Drops & Install Casework
[35 empty] | 12 | Countertops, Millwork & Final Paint
[35 empty] | 13 | Walls & Casework Fixtures, Ceiling Tiles & Flooring
[35 empty] | 14 | Flooring, Final Paint & 1st Clean
[35 empty] | 15 | Punchlist, Corrections & Final Clean
JANUARY |  |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  | MAY |  |  |  |  | JUNE |  |  |  | JULY
Zone 1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
| Zone 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
|  | Zone 3 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Zone 1 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | 9
[5 empty] | Zone 2 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7
[10 empty] | Zone 3 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5
[15 empty] | Zone 4 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4
[20 empty] | Zone 5 | 1 | 1 | 1 | 2 | 2
JANUARY |  | FEBRUARY 5 4 3: FEBRUARY; MARCH 9 8 7: MARCH; APRIL 13 12 11: APRIL; MAY 17 16 15: MAY; JUNE 22 21 20: JUNE; JUNE 25 25 24: JULY
Zone 1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| Zone 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
|  | Zone 3 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
|  |  | Zone 4 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
|  |  |  | Zone 5 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Start Here
Interiors
Interiors
Optimazing Takt Plan in the Macro Level
4 Week Look Ahead
Start Here
Zone Map
Interiors Legend
Zone Map
Interiors Legend
Scan QR Code Below With Smart Phone Camera
Buffer
Rules of Thumb:
1. Check the plan with your calculator
2. Check the shape
3. Check for conservative or aggressive packaging
4. Check for the balance between divisions and additions
1
2
3
4
Buffers
Step 1: Check Rules of Thumb
1
Step 2: Optimization
2
Step 3: Repackage
3
Step 4: Map Out The Optimized Takt Plan Including Buffers
4
Steps Summary:

## One Floor Norm Example
2022 | [19 empty] | 2023 | [129 empty] | 2024 | [261 empty] | 2025 | [260 empty] | 2026 | [260 empty] | 2027
December | [19 empty] | January | [21 empty] | February | [19 empty] | March | [22 empty] | April | [19 empty] | May | [22 empty] | June | [21 empty] | January | [22 empty] | February | [20 empty] | March | [20 empty] | April | [21 empty] | May | [22 empty] | June | [19 empty] | July | [22 empty] | August | [21 empty] | September | [20 empty] | October | [22 empty] | November | [20 empty] | December | [21 empty] | January | [22 empty] | February | [19 empty] | March | [20 empty] | April | [21 empty] | May | [21 empty] | June | [20 empty] | July | [22 empty] | August | [20 empty] | September | [21 empty] | October | [22 empty] | November | [19 empty] | December | [22 empty] | January | [21 empty] | February | [19 empty] | March | [21 empty] | April | [21 empty] | May | [20 empty] | June | [21 empty] | July | [22 empty] | August | [20 empty] | September | [21 empty] | October | [21 empty] | November | [20 empty] | December | [22 empty] | January | [21 empty] | February | [19 empty] | March | [21 empty] | April | [21 empty] | May | [20 empty] | June | [21 empty] | July | [22 empty] | August | [20 empty] | September | [21 empty] | October | [21 empty] | November | [20 empty] | December
2022-12-05 | 2022-12-06 | 2022-12-07 | 2022-12-08 | 2022-12-09 | 2022-12-12 | 2022-12-13 | 2022-12-14 | 2022-12-15 | 2022-12-16 | 2022-12-19 | 2022-12-20 | 2022-12-21 | 2022-12-22 | 2022-12-23 | 2022-12-26 | 2022-12-27 | 2022-12-28 | 2022-12-29 | 2022-12-30 | 2023-01-02 | 2023-01-03 | 2023-01-04 | 2023-01-05 | 2023-01-06 | 2023-01-09 | 2023-01-10 | 2023-01-11 | 2023-01-12 | 2023-01-13 | 2023-01-16 | 2023-01-17 | 2023-01-18 | 2023-01-19 | 2023-01-20 | 2023-01-23 | 2023-01-24 | 2023-01-25 | 2023-01-26 | 2023-01-27 | 2023-01-30 | 2023-01-31 | 2023-02-01 | 2023-02-02 | 2023-02-03 | 2023-02-06 | 2023-02-07 | 2023-02-08 | 2023-02-09 | 2023-02-10 | 2023-02-13 | 2023-02-14 | 2023-02-15 | 2023-02-16 | 2023-02-17 | 2023-02-20 | 2023-02-21 | 2023-02-22 | 2023-02-23 | 2023-02-24 | 2023-02-27 | 2023-02-28 | 2023-03-01 | 2023-03-02 | 2023-03-03 | 2023-03-06 | 2023-03-07 | 2023-03-08 | 2023-03-09 | 2023-03-10 | 2023-03-13 | 2023-03-14 | 2023-03-15 | 2023-03-16 | 2023-03-17 | 2023-03-20 | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-24 | 2023-03-27 | 2023-03-28 | 2023-03-29 | 2023-03-30 | 2023-03-31 | 2023-04-03 | 2023-04-04 | 2023-04-05 | 2023-04-06 | 2023-04-07 | 2023-04-10 | 2023-04-11 | 2023-04-12 | 2023-04-13 | 2023-04-14 | 2023-04-17 | 2023-04-18 | 2023-04-19 | 2023-04-20 | 2023-04-21 | 2023-04-24 | 2023-04-25 | 2023-04-26 | 2023-04-27 | 2023-04-28 | 2023-05-01 | 2023-05-02 | 2023-05-03 | 2023-05-04 | 2023-05-05 | 2023-05-08 | 2023-05-09 | 2023-05-10 | 2023-05-11 | 2023-05-12 | 2023-05-15 | 2023-05-16 | 2023-05-17 | 2023-05-18 | 2023-05-19 | 2023-05-22 | 2023-05-23 | 2023-05-24 | 2023-05-25 | 2023-05-26 | 2023-05-29 | 2023-05-30 | 2023-05-31 | 2023-06-01 | 2023-06-02 | 2023-06-05 | 2023-06-06 | 2023-06-07 | 2023-06-08 | 2023-06-09 | 2023-06-12 | 2023-06-13 | 2023-06-14 | 2023-06-15 | 2023-06-16 | 2023-06-19 | 2023-06-20 | 2023-06-21 | 2023-06-22 | 2023-06-23 | 2023-06-26 | 2023-06-27 | 2023-06-28 | 2023-06-29 | 2023-06-30 | time axis 2024-01-01 to 2027-12-31
M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | time axis 2024-01-01 to 2027-12-31
[30 empty] | Zone 1 | 1 | 1 | 1 | 2 | 2 | 2 | B | B | B | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | B | B | B | B | 11 | 11 | 11 | B | B | B | 12 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 15 | 15 | 15
[33 empty] | Zone 2 | 1 | 1 | 1 | 2 | 2 | 2 | B | B | B | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | B | B | B | B | 10 | 10 | 10 | 11 | 11 | 11 | B | B | B | 12 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | B | B | B | B | 15 | 15 | 15
[10 empty] | 1 | Remove re-shores, Floor Prep, Final Patch Ceiling & Layout Walls | [18 empty] | Remove Reshores | [5 empty] | Zone 3 | 1 | 1 | 1 | 2 | 2 | 2 | B | B | B | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | B | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | B | B | B | 12 | 12 | 12 | 13 | 13 | 13 | B | B | B | B | 14 | 14 | 14 | 15 | 15 | 15
[10 empty] | 2 | Install Fire Sprinkler Main and Branch Lines & Install Priority Walls | [27 empty] | Zone 4 | 1 | 1 | 1 | 2 | 2 | 2 | B | B | B | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | B | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | B | B | B | 12 | 12 | 12 | B | B | B | B | 13 | 13 | 13 | 14 | 14 | 14 | 15 | 15 | 15
[10 empty] | 3 | OH Mechanical | [30 empty] | Zone 5 | 1 | 1 | 1 | 2 | 2 | 2 | B | B | B | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | B | B | B | B | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | B | B | B | B | B | B | B | 12 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 15 | 15 | 15
[10 empty] | 4 | OH Mechanical, OH Plumbing | [33 empty] | Zone 6 | 1 | 1 | 1 | 2 | 2 | 2 | B | B | B | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | B | B | B | B | B | B | B | 12 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 15 | 15 | 15
[10 empty] | 5 | OH Electrical & Frame Walls | [36 empty] | Zone 7 | 1 | 1 | 1 | 2 | 2 | 2 | B | B | B | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | B | B | B | B | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | B | B | B | B | 11 | 11 | 11 | B | B | B | 12 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 15 | 15 | 15
[10 empty] | 6 | In-wall Electrical & Plumbing | [39 empty] | Zone 8 | 1 | 1 | 1 | 2 | 2 | 2 | B | B | B | 3 | 3 | 3 | 4 | 4 | 4 | B | B | B | B | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | B | B | B | B | 10 | 10 | 10 | 11 | 11 | 11 | B | B | B | 12 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 15 | 15 | 15
[10 empty] | 7 | In-wall Piping, One-side Dry Wall & In-wall Inspection | [42 empty] | Zone 9 | 1 | 1 | 1 | 2 | 2 | 2 | B | B | B | 3 | 3 | 3 | B | B | B | B | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | B | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | B | B | B | 12 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 15 | 15 | 15
[10 empty] | 8 | Second Side Dry Wall, Insulation & Finish Walls | [45 empty] | Zone 10 | 1 | 1 | 1 | 2 | 2 | 2 | B | B | B | B | B | B | B | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | B | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | B | B | B | 12 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 15 | 15 | 15
[10 empty] | 9 | Prime 1st & 2nd Coat Paint | [48 empty] | Zone 11 | 1 | 1 | 1 | 2 | 2 | 2 | B | B | B | B | B | B | B | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | B | B | B | B | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | B | B | B | 12 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 15 | 15 | 15 | B | B | B | B | B | B | B | B | B | B | B | B | B | B | B | B | B | B
[10 empty] | 10 | Ceiling Grid, Lights, Electrical Fixtures & Mechanical Ceiling Drops | [63 empty] | Start Drywall | [5 empty] | Power On | [26 empty] | Air On |  |  |  |  | Fianal Clean | [10 empty] | Additional Buffer or Time Gained | [16 empty] | Contractual Substantial Completion and Financial Target
[10 empty] | 11 | Casework & Final Pain (Possible) | [113 empty] | Target Substantial Completion | [5 empty] | Target Final Completion
[10 empty] | 12 | Millwork, Plumbing, Wall and Casework, Ceiling Tiles | [28 empty] | Erect Stair
[10 empty] | 13 | Flooring | [32 empty] | Pour Stair Pans
[10 empty] | 14 | Final Paint, Final Clean 1st Pass & Incomplete Worklist | [37 empty] | Erect Stair
[10 empty] | 15 | Arch Punchlist, Corrections & Final Clean | [41 empty] | Pour Stair Pans
[75 empty] | Temp Roof |  |  |  |  | Install Swing Stages
Set AHU & Install
Zone 1-4
[11 empty] | Weather Risk | [7 empty] | 3 | [77 empty] | Zone 5-8
[11 empty] | Manpower not available | [7 empty] | 5 | [83 empty] | Zone 9-11
[11 empty] | Procurement Issues | [7 empty] | 5 | [83 empty] | B | B | B | B | B
[11 empty] | Shortage in crew | [7 empty] | 2
[11 empty] | Contractor labor not ready | [7 empty] | 8 | [32 empty] | Shaft Prep
[11 empty] | Higher risk | [7 empty] | 8 | [36 empty] | Elevator Cabs
Test + Certification
Pre-Functional Checklists
Controls
TAB
Commissioning
Fire Life Safety
[118 empty] | Final Walks |  |  |  |  | B
Interiors
Neuroscience Institute Takt Plan
Logistics Map
Zone Map
Start Here
Need Help in Reading this Takt Plan?
Scan QR Code Below With Smart Phone Camera
Risk Analysis
Interior Legend
6 Week Look Ahead
WWP

## One Floor Weekly Work Plan Expl
WEEKLY WORK PLAN (JAN 16-20) |  |  |  |  | 16 | 17 | 18 | 19 | 20
PHASE | ZONE | TRADE | # | ACTIVITY | M | T | W | T | F
Interiors | All Building
| Zone 1 | Framing | 1 | Remove re-shores, Floor Prep, Final Patch Ceiling & Layout Walls | [6 empty] | Friday
|  | FS | 2 | Install Fire Sprinkler Main and Branch Lines & Install Priority Walls | [7 empty] | Handover | Succesor
| Zone 2 | Framing | 1 | Remove re-shores, Floor Prep, Final Patch Ceiling & Layout Walls | [5 empty] | Interiors Z1
| Zone 3 | [10 empty] | 1 | 2
Zone 4
| Zone 5 | [8 empty] | Interiors Z2
| Zone 6 | [11 empty] | 1
Zone 7
Zone 8
Zone 9
Zone 10
Zone 11
Zone Map
Interior Legend
Handoffs

## Procurement
|  |  | Procurement Log | [18 empty] | Today: | 2024-02-20
[22 empty] | Week of the year: | 8
Spec Section | Scope of Work | Takt Zone | Trade Partner | Drop Dead Subcontract Execution | Subcontract Executed | Submittal Prep WKS | Receive Submittal | Actual Approved Submittal | Submittal Review WKS | Sent To Design Team | Design Approved | Design Team Approval Wks. | Release Date | Confirmed Release Date | Submittal Over/Under Days | Lead Time WKS | Ship Date | Delivery Weeks | Buffer Duration WEEKS | Actual Date on Site | Required On Job (Get Superintendent Input!) | Material Over/Under DAYS | Notes | Last Date of Contact
Toggle Light Switches | Electrical | 2 | Electrical Services | 2023-09-07 |  | 1 | 2023-09-14 |  | 1 | 2023-09-21 |  | 1 | 2023-09-28 |  |  | 5 | 2023-11-02 | 1 | 1 |  | 2023-11-16
Duplex Receptacles | Electrical | 2 | Electrical Services | 2023-10-12 |  | 0 | 2023-10-12 |  | 0 | 2023-10-12 |  | 0 | 2023-10-12 |  |  | 3 | 2023-11-02 | 2 | 0 |  | 2023-11-16
Recessed lighting | Electrical | 2 | Electrical Services | 2023-09-14 |  | 0 | 2023-09-14 |  | 0 | 2023-09-14 |  | 0 | 2023-09-14 |  |  | 5 | 2023-10-19 | 2 | 2 |  | 2023-11-16
Cabinets | Casework | 2 | Cabintes & More LLC | 2023-08-01 |  | 0 | 2023-08-01 |  | 0 | 2023-08-01 |  | 0 | 2023-08-01 |  |  | 14 | 2023-11-07 | 3 | 0 |  | 2023-11-28 |  |  |  | Spec Section | Scope of Work | Takt Zone | Trade Partner | Drop Dead Release TP Date | Actual Released TP For Submittal | Submittal Prep WKS | Receive Submittal | Submittal Review WKS | Sent To Design Team | Design Team Approval Wks. | Actual Approved Submittal | Required Submittal Approval | Submittal Over/Under Days | Lead Time WKS | Ship Date | Delivery Weeks | Buffer Duration WEEKS | Actual Date on Site | Required On Job (Get Superintendent Input!) | Material Over/Under DAYS | Comments (Issues, who needs the approved submittal, etc.)
Drawers | Casework | 2 | Cabintes & More LLC | 2023-10-10 | 2023-09-30 | 0 | 2023-10-10 |  | 0 | 2023-10-10 |  | 0 | 2023-10-10 |  | -10 | 4 | 2023-11-07 | 2 | 1 |  | 2023-11-28
Bookshelves | Casework | 2 | Cabintes & More LLC | 2023-10-03 |  | 0 | 2023-10-03 |  | 0 | 2023-10-03 |  | 0 | 2023-10-03 |  |  | 7 | 2023-11-21 | 1 | 0 |  | 2023-11-28 |  |  |  | Spec Section | Scope of Work | Takt Zone | Trade Partner | Drop Dead Subcontract Execution | Subcontract Executed | Submittal Prep WKS | Receive Submittal | Submittal Review WKS | Received Submittal Date | Release Date | Actual Approved Submittal | Confirmed Release Date | Submittal Over/Under Days | Lead Time WKS | Ship Date | Delivery Weeks | Buffer Duration WEEKS | Actual Date on Site | Required On Job (Get Superintendent Input!) | Material Over/Under DAYS | Notes | Last Date of Contact
Windows | Millwork | 2 | Doors & Windows Inc | 2023-08-30 |  | 0 | 2023-08-30 |  | 0 | 2023-08-30 |  | 0 | 2023-08-30 |  |  | 8 | 2023-10-25 | 5 | 1 |  | 2023-12-06
Doors | Millwork | 2 | Doors & Windows Inc | 2023-10-11 |  | 0 | 2023-10-11 |  | 0 | 2023-10-11 |  | 0 | 2023-10-11 |  |  | 4 | 2023-11-08 | 3 | 1 |  | 2023-12-06
Light Fixtures | Electrical | 2 | Electrical Services | 2023-06-22 |  | 0 | 2023-06-22 |  | 0 | 2023-06-22 |  | 0 | 2023-06-22 |  |  | 20 | 2023-11-09 | 1 | 0 |  | 2023-11-16
Electric Sockets | Electrical | 2 | Electrical Services | 2023-10-05 |  | 0 | 2023-10-05 |  | 0 | 2023-10-05 |  | 0 | 2023-10-05 |  |  | 3 | 2023-10-26 | 2 | 1 |  | 2023-11-16
Security Alarm System | Electrical | 2 | Electrical Services | 2023-10-19 |  | 0 | 2023-10-19 |  | 0 | 2023-10-19 |  | 0 | 2023-10-19 |  |  | 2 | 2023-11-02 | 2 | 0 |  | 2023-11-16
Fire Alarm | Electrical | 2 | Electrical Services | 2023-10-05 |  | 0 | 2023-10-05 |  | 0 | 2023-10-05 |  | 0 | 2023-10-05 |  |  | 2 | 2023-10-19 | 2 | 2 |  | 2023-11-16
Kitchens | Casework | 2 | Kitchens Inc | 2023-08-31 |  | 0 | 2023-08-31 |  | 0 | 2023-08-31 |  | 0 | 2023-08-31 |  |  | 10 | 2023-11-09 | 2 | 1 |  | 2023-11-30
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 2 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
**ITEMS IN RED ARE IN TROUBLE** | [22 empty] | LAST DATE REVIEWED W/ SUPER:
Formulas:
Drop Dead Subcontract Execution = IF([Receive Submittal]="","",[Receive Submittal]-(7*[Submittal Prep WKS]))
Receive Submittal = IF([Sent To Design Team]="","",[Sent To Design Team]-([Submittal Review WKS]*7))
Receive Submittal = IF([Release Date]="","",[Release Date]-([Submittal Review WKS]*7))
Sent To Design Team = IF([Release Date]="","",[Release Date]-([Design Team Approval Wks.]*7))
Release Date = IF([Ship Date]="","",[Ship Date]-(7*[Lead Time WKS]))
Ship Date = IF(W5="","",W5-(7*[Delivery Weeks])-(7*[Buffer Duration WEEKS]))
1
How to use Procurement Log:
1. Fill in the Spec Section, Scope of Work, Takt Zone and Trade Partner.
2. Start with the "Required on Job" date (you can obtain this from the norm-level takt plan).
3. Fill in the estimated delivery weeks and if considered, the buffer weeks.
4. Ship Dates will be updated automatically.
5. Add the Lead Time Weeks. (Required Submittal Approval will update automatically).
6. Fill in addtional work weeks such as Submittal Prep & Review WKS and "Design Team Approval WKS.
7. When the actual Released TP and Approved Submittal date is obtained, it is necesasay to fill it in manually.
NOTES: Only the "Required on Job" date is necessary to fill in, the other dates will update according the added information. Comment section can be used for special considerations or additional conditions for the log entry.
2
3
6
7
4
5
1
3
2
7
1
2
3
6
7
7
4
5
1
3
2
6
4
7
5
Information Needed
Automatically
Green = More than 2 weeks from Today
Yellow = 1-14 Days from Today
Red = The Date was not achieved

## Roadblocks
Roadblock Tracking and Removal Log
No. | Roadblock | Zone | Date Added | Affected Activity | Who is on Point | Classification | Critical Date | Count Down (Days) | Date Resolved | Process Time | Score | Details/ Notes | Dashboard
1 | Roadblock 1 | Zone 1 | 2024-01-10 | Activity X | Person 1 | Classification 4 | 2024-01-22 | -29 |  | In Progress |  |  | Roadblock < 7 Days to Critical | 0
[13 empty] | Uncleared Roadblocks | 0
[13 empty] | Cleared Roadblocks | 0
[13 empty] | Average Process Time | #DIV/0!
[13 empty] | Score | #DIV/0!
[13 empty] | List for Who is on Point | List for Classification
[13 empty] | Person 1 | General
[13 empty] | Person 2 | MEP
[13 empty] | Person 3 | Design
[13 empty] | Person 4 | Classification 4
[13 empty] | Person 5 | Classification 5
Classification 6
#DIV/0!
Formulas:
Count Down (Days) = IFS([Date Added]="","",[Date Resolved]="",[Critical Date]-TODAY(),[Date Resolved]>0,[Date Resolved]-[Date Added])

## Risk & Opp
PROJECT NAME
Cost Risk-Opportunity Analysis
| Identified Risks/Opportunities | Liquidated Damages Cost per Day | #
| RISK | Project Impact/consequences |  | Impact in Days | Costs | Action Plan-Solutions |  | Cost Analysis | OPUR
1 | Risk 1 | Description | [5 empty] | 0
2 | Risk 2 | Description | [5 empty] | 0
3 | Risk 3 | Description | [5 empty] | 0
4 | Risk 4 | Description | [5 empty] | 0
5 | [7 empty] | 0
6 | [7 empty] | 0
7 | [7 empty] | 0
8 | [7 empty] | 0
9 | [7 empty] | 0
10 | [7 empty] | 0
11 | [7 empty] | 0
12 | [7 empty] | 0
13 | [7 empty] | 0
14 | [7 empty] | 0
15 | [7 empty] | 0
16 | [7 empty] | 0
17 | [7 empty] | 0
[7 empty] | Total Risk Cost | 0
| OPPORTUNITIES | Project Impact/Consequences |  | Impact in Days | Costs | Action Plan-Solutions |  | Cost Analysis | OPUR
1 | Opp 1 | Description | [5 empty] | 0
2 | Opp 2 | Description | [5 empty] | 0
3 | Opp 3 | Description | [5 empty] | 0
4 | Opp 4 | Description | [5 empty] | 0
5 | [7 empty] | 0
6 | [7 empty] | 0
7 | [7 empty] | 0
8 | [7 empty] | 0
9 | [7 empty] | 0
10 | [7 empty] | 0
11 | [7 empty] | 0
12 | [7 empty] | 0
13 | [7 empty] | 0
14 | [7 empty] | 0
15 | [7 empty] | 0
16 | [7 empty] | 0
17 | [7 empty] | 0
OPUR>One Person Ultimately Responsible
[7 empty] | Total opportunity Gain | 0
[7 empty] | Difference in risk vs opportunity | 0

## Parametrics Calculator
Takt Value Parametric
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | [8 empty] | 49 | Used Takt Wagons
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | [7 empty] | 42 | Empty Takt Wagons
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 |  |  |  |  | 1.1667 |  |  | The Value Parameter
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
Takt Efficiency Parametric
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | [8 empty] | 7 | Takt Wagons
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | [7 empty] | 7 | Takt Sequences
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 |  |  |  |  | 1 |  |  | The Efficiency Parameter
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
Takt Stability Parametric
1 | 2 | 3 | 4 | B | 5 | 6 | 7 |  | B
| 1 | 2 | 3 | 4 | B | 5 | 6 | 7 | B
|  | 1 | 2 | 3 | 4 | B | 5 | 6 | B | 7 | [9 empty] | 2 | Takt Buffers
|  |  | 1 | 2 | 3 | 4 | B | 5 | B | 6 | 7 | [8 empty] | 3 | End Buffers
|  |  |  | 1 | 2 | 3 | 4 | B | B | 5 | 6 | 7 | [6 empty] | 0.66667 |  | The Takt Stability Parameter
[5 empty] | 1 | 2 | 3 | 4 | B | B | 5 | 6 | 7
[6 empty] | 1 | 2 | 3 | B | 4 | B | 5 | 6 | 7 | B | B | B
Takt Value Parametric
|  |  |  | Used Takt Wagons | [7 empty] | #REF!
|  |  |  | Empty Takt Wagons | [7 empty] | #REF!
[12 empty] | #REF! |  |  |  | #REF!
Takt Efficiency Parametric
|  |  |  | Takt Wagons | [7 empty] | #REF!
|  |  |  | Takt Sequences | [7 empty] | 11
[12 empty] | #REF! |  |  |  | #REF!
Takt Stability Parametric
|  |  |  | Takt Buffers | [7 empty] | #REF!
|  |  |  | End Buffers | [7 empty] | #REF!
[12 empty] | #REF! |  |  |  | #REF!
Takt Parametrics

## SOS
Schedule of a Schedule
|  | Schematic Design | [9 empty] | Design Development | [7 empty] | Construction Documentation | [7 empty] | Notice to Proceed / Guaranteed Maximum Price
|  | 96.11% | [9 empty] | 42.36% | [7 empty] | 3.472% | [7 empty] | 0%
|  | SD Design Complete | Pre-con Team Formed | Document Review & Study | Basis of Schedule | Create Takt Zone Maps | Initial Macro Takt Plan Created | If required create another format of the schedule for contract inclusion. | General Super Review of Plan | GC GR Review | Finalize Cost Model | DD Design Complete | Project Team is identified | Refine Takt Zone Maps | Refine Macro Takt Plan | Site Logistics Plan | Create Procurement Log & Supply Chain Meetings | geographical analysis | Revise Cost Model per Plan | CD Design Complete | Refine Takt Zone Maps | Refine Macro Takt Plan with Full Buffer Management | Site Logistics Plan | RISK ANALYSIS (add final buffer management to takt plan) | Operational Excellence Plan | Conditions of Satisfaction | Revise Cost Model per Plan | Fresh Eyes | Adjust Plan per the Fresh Eye Comments. | Attach as addendum to contract | Road Block Tracking System Working (6 week lookahead) | Create Work Steps | Takt Health | Printed Logistics + Takt Zone Maps | Roadblock Removal System in Place | Tracking KPIs | Add TPNR | Meeting Systems in place | Change Management Review | Communication to Owner | CPM Carbon Copy System live
|  | Person 1 | Person 2 | Person 3 | Person 4 | Person 5 | Person 6 | Person 7 | Person 8 | Person 9 | Person 10
Building A |  | Person 1: 100% |  | 54.17% | [7 empty] | 6.944% | [7 empty] | 0% | [13 empty] | List for Who is on Point
57.5% | Phase A | [9 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [17 empty] | Person 1 | bar: Person 1 to Person 9
40% | Phase B | [9 empty] | x | x | x | x | x | x | x | [24 empty] | Person 2 | bar: Person 1 to Person 9
37.5% | Phase C | [9 empty] | x | x | x | x | x | x | [25 empty] | Person 3 | bar: Person 1 to Person 9
37.5% | Phase D | [9 empty] | x | x | x | x | x | x | [25 empty] | Person 4 | bar: Person 1 to Person 9
35% | Phase E | [9 empty] | x | x | x | x | x | [26 empty] | Person 5 | bar: Person 1 to Person 9
32.5% | Phase F | [9 empty] | x | x | x | x | [27 empty] | Person 6 | bar: Person 1 to Person 9
32.5% | Phase G | [9 empty] | x | x | x | x | [27 empty] | Person 7 | bar: Person 1 to Person 9
32.5% | Phase H | [9 empty] | x | x | x | x | [27 empty] | Person 8 | bar: Person 1 to Person 9
30% | Phase I | [9 empty] | x | x | x | [28 empty] | Person 9 | bar: Person 1 to Person 9
Person 10
Building B |  | Person 1: 92.22% |  | 30.56% | [7 empty] | 0% | [7 empty] | 0%
42.5% | Phase A | [9 empty] | x | x | x | x | x | x | x | x | bar: Person 1 to Person 9
40% | Phase B | [9 empty] | x | x | x | x | x | x | x | bar: Person 1 to Person 9
37.5% | Phase C | [9 empty] | x | x | x | x | x | x | bar: Person 1 to Person 9
32.5% | Phase D | [9 empty] | x | x | x | x | bar: Person 1 to Person 9
27.5% | Phase E | [9 empty] | x | x | bar: Person 1 to Person 9
25% | Phase F | [9 empty] | x | bar: Person 1 to Person 9
20% | Phase G | bar: Person 1 to Person 8
20% | Phase H | bar: Person 1 to Person 8
17.5% | Phase I | bar: Person 1 to Person 7